## Sheet1
Procurement Monitoring Report as of June 30,2023
ZAMBOANGA SIBUGAY POLYTECHNIC INSTITUTE
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| OFFICIAL RECEIPT FOR CASHIER OFFICE | [19 empty] | ROMEE A TAMSI | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | N/A | 2023-06-02 | 2023-06-02 | GOP | 50000 | 50000 | N/A | 50000 | 50000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | completed
| CONSUMABLES FOR ASSESSMENT IN FOOD PROCESSING COC1- PTC/BUUG | [19 empty] | AMY N. MABATID | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | N/A | 2023-03-02 | 2023-03-02 | GOP | 5724.5 | 5724.5 | N/A | 609 | 609 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | completed
| CONSUMABLES FOR ASSESSMENT IN FOOD PROCESSING COC1- PTC/BUUG | [19 empty] | AMY N. MABATID | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | N/A | 2023-03-02 | 2023-03-02 | GOP | 5724.5 | 5724.5 | N/A | 512.65 | 512.65 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | completed
| MEALS & SNACKS FOR OFFICE COMMITMENT AND REVIEW (OPCR) VALIDATION | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-09 | 2023-01-09 | GOP | 41000 | 41000 | N/A | 41000 | 41000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | completed
| FOR OFFICE SUPPLIES (3RD QUARTER)- ADMIN | [19 empty] | LYNDRE G. BAYOTAS | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-02-20 | 2023-03-06 | 2023-03-06 | GOP | 634050 | 634050 | N/A | 531815 | 531815 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-02-14 | completed
| CONSUMABLES FOR T-SHIRT PRINTING OF ZSPI TRAINEES | [19 empty] | MALARE P. COTEJO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | 2023-02-09 | N/A | 2023-02-02 | 2023-02-02 | GOP | 4,00.00 | 4,00.00 | N/A | 3000 | 3000 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | N/A | 2023-02-02 | completed
| COMMUNITTY BASED TRAINING FOR TABLE SKIRTING ON FEB, 22,2023 | [19 empty] | MAY P. COMEDIDO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-14 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GOP | 3000 | 3000 | N/A | 2120 | 2120 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-07 | completed
| NATIONAL ASSESSMENT FOR BARTENDING NCII-ZSPI DIPLOMA | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-02-13 | 2023-03-09 | GOP | 47939 | 47939 | N/A | 296 | 296 | N/A | N/A | N/A | 2023-03-08 | 8/3/23. | 8/3.23 | 2023-03-08 | 2023-03-09 | Completed
| NATIONAL ASSESSMENT FOR BARTENDING NCII-ZSPI DIPLOMA(20 CANDIDATES) | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | 2023-03-10 | GOP | 47939 | 47939 | N/A | 11694 | 11694 | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-10 | completed
| NATIONAL ASSESSMENT FOR BARTENDING NCII-ZSPI DIPLOMA(20 CANDIDATES) | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | 2023-03-10 | GOP | 47939 | 47939 | N/A | 6314 | 6314 | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-14 | completed
| FOR OFFICE SUPPLIES ASSESSMENT (3RD AND 4TH QUARTER) & REPLACEMENT OF CCTV PARTS (DAMAGE) AND MAINTENANCE FOR ASSESSMENT | [19 empty] | AMY N. MABATID | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-15 | 2023-02-16 | 2023-02-20 | 2023-03-17 | 2023-03-17 | GOP | 551490 | 551490 | N/A | 111100 | 111100 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-03-17 | completed
| CONSUMABLES FOR ASSESSMENT IN FOOD PROCESSING COC1- PTC/BUUG | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | 2023-01-24 | 2023-01-24 | 2023-01-25 | N/A | 2023-03-02 | 2023-03-02 | GOP | 5674.5 | 5674.5 | N/A | 3840 | 3840 | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | 2023-03-02 | completed
| TRAINING CONSUMABLES, TOOLS AND EQUIPMENT FOR PHILIPPINE NATIONAL SKILLS COPMPETITION 2023(COOKERY) | [19 empty] | GRETCHEN J.NUBOG | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-02-20 | 2023-02-17 | 2023-02-17 | 2023-02-21 | 2023-02-23 | 2023-03-18 | 2023-03-18 | GOP | 89819 | 89819 | N/A | 13998 | 13998 | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-02-20 | 2023-03-18 | completed
| CONSUMABLES FOR PICHI-PICHI FOR ONE DAY SKILLS TRAINING @ R.T. LIM, ZSP 13,2023 | [19 empty] | JENEBELLE T. CONAHAP | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 | GOP | 2555 | 2555 | N/A | 2008 | 2008 | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-13 | completed
| CONSUMABLES FOR COMMUNITY BASE TRAINING FOR BODY MASSAGE @ R.T. ZSP APRIL 13, 2023 | [19 empty] | ELMA E. GAJOSTA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 | GOP | 3080 | 3080 | N/A | 3049 | 3049 | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-13 | completed
| FOR USE IN OFFICIAL VEHICLE MAINTENANCE NAVARA GAN 2367 | [19 empty] | EDUARDO A. PEPINO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | 2023-01-18 | 2023-02-07 | 2023-01-18 | 2023-01-18 | 2023-02-08 | 2023-02-10 | 2023-04-12 | 2023-04-12 | GOP | 38950 | 38950 | N/A | 30624 | 30624 | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | 2023-03-23 | 2023-02-07 | 2023-04-12 | completed
| COMMUNITY BASED TRAINING FOR BANANA BREAD MAKING @ ALICIA, ZBG.SIBUGAY | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-03-10 | 2023-03-10 | 2023-03-11 | 2023-03-11 | GOP | 1648 | 1648 | N/A | 1573 | 1573 | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-03-23 | 2023-03-11 | completed
| LUNCH FOR PRE-BID CONFERENCE ON THE PROVISION OF SECURITY | [19 empty] | ANALYN J. ELLORINE | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-05-11 | 2023-03-29 | 2023-05-11 | 2023-05-15 | 2023-05-15 | 2023-05-17 | 2023-05-17 | GOP | 2250 | 2250 | N/A | 2250 | 2250 | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-05-11 | 2023-05-17 | completed
| OFFICE SUPPLIES, HARDWARE SURPLIES, MEDICAL/RESCUE EQUIPMENT, & TARPAULIN, BANNER & SIGNAGES FOR ZSPI ROTC | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-11 | 2023-05-19 | 2023-05-15 | 2023-05-30 | 2023-05-30 | GOP | 41735 | 41735 | N/A | 8005 | 8005 | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-16 | 2023-05-30 | completed
| OFFICE SUPPLIES, HARDWARE SURPLIES, MEDICAL/RESCUE EQUIPMENT, & TARPAULIN, BANNER & SIGNAGES FOR ZSPI ROTC | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-11 | 2023-05-19 | 2023-05-15 | 2023-05-30 | 2023-05-30 | GOP | 41735 | 41735 | N/A | 2803 | 2803 | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-16 | 2023-05-30 | completed
| COMMUNITY BASED TRAINING FOR BANANA BREAD MAKING @ ALICIA, ZBG.SIBUGAY | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | N/A | 2023-03-08 | N/A | 2023-03-09 | N/A | 2023-05-25 | 2023-05-25 | GOP | 1603 | 1603 | N/A | 1448 | 1448 | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | N/A | 2023-05-25 | completed
| COMMUNITY BASED TRAINING FOR BANANA CAKE & BUKO PIE MAKING @ IPIL , ZBG.SIBUGAY | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-03-09 | N/A | 2023-03-09 | 2023-03-09 | 2023-03-09 | N/A | 2023-03-13 | 2023-03-13 | GOP | 3335 | 3335 | N/A | 2921 | 2921 | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-03-09 | N/A | 2023-03-13 | completed
| OFFICE SUPPY HARDWARE SUPPLIES, MEDICAL/RESCUE EQUIPMENT, & TARPAULIN, BANNER & SINAGES FOR ZSPI ROTC | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | 2023-03-15 | 2023-03-16 | 2023-05-19 | N/A | 2023-05-30 | 2023-05-30 | GOP | 41735 | 41735 | N/A | 8100 | 8100 | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | 2023-05-30 | completed
| TOOLS AND MATERIALS FOR SKILLS TRAINING COMMUNITY BASED IN TAILORING - R.T. LIM | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-03-16 | 2023-05-12 | 2023-05-11 | 2023-04-13 | 2023-04-13 | GOP | 9898 | 9898 | N/A | 9617 | 9617 | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-04-13 | completed
| MEALS AND SNACKS FOR SCHOLARSHIP REVIEW | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-01-06 | 2023-01-06 | 2023-01-10 | 2023-01-10 | GOP | 17500 | 17500 | N/A | 17500 | 17500 | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-01-10 | completed
| CONSUMBLES FOR ASSESSMENT IN FOOD PROCESSING COC1- PTC/BUUG 25 CANDIDATES | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | 2023-01-24 | N/A | 2023-01-25 | N/A | 2023-02-03 | 2023-02-03 | GOP | 5724.5 | 5724.5 | N/A | 512 | 512 | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | 2023-02-03 | completed
| CONSUMABLES FOR ASSESSMENT IN FOOD PROCESSING COC1- PTC/BUUG | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | 2023-01-24 | N/A | 2023-01-25 | N/A | 2023-02-03 | 2023-02-03 | GOP | 5724.5 | 5724.5 | N/A | 609 | 609 | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-01-24 | N/A | 2023-02-03 | completed
| MEALS AND SNACKS OF NATIONAL COMPETENCY ASSESSMENT | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | 2023-02-13 | N/A | 2023-01-25 | N/A | 2023-02-21 | 2023-02-21 | GOP | 15900 | 15900 | N/A | 15900 | 15900 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | 2023-02-21 | completed
| COSTUME FOR EDUCATOR'S NIGHT | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | N/A | 2023-02-02 | N/A | 2023-03-02 | N/A | 2023-02-06 | 2023-02-06 | GOP | 42900 | 42900 | N/A | 42900 | 42900 | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2023-02-02 | N/A | 2023-02-06 | completed
| FOR OFFICE SUPPLIES ASSESSMENT (3RD AND 4TH QUARTER) & REPLACEMENT OF CCTV PARTS (DAMAGE) AND MAINTENANCE FOR ASSESSMENT | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-02-15 | 2023-03-02 | 2023-02-20 | 2023-04-11 | 2023-04-11 | GOP | 551490 | 551490 | N/A | 193035 | 193035 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-04-11 | completed
| MEALS AND SNACKS FOR ZSPI INTERNAL AUDIT | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-02-15 | 2023-02-03 | 2023-02-15 | 2023-03-02 | 2023-03-03 | 2023-03-07 | 2023-03-07 | GOP | 21800 | 21800 | N/A | 21800 | 21800 | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-02-15 | 2023-03-07 | completed
| CONSUMABLES AND TOOLS FOR COMPLIANCE AUDIT IN AGRICULTURE CROPS PRODUCTION NC II | [19 empty] | MAE JANE G. DAGUPAN | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-04-13 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-18 | 2023-04-28 | 2023-04-28 | GOP | 145640 | 145640 | N/A | 143018 | 143018 | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-04-13 | 2023-04-28 | completed
| ASSESSMENT CENTER- XEROX MACHINE MAINTENANCE USE | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-20 | 2023-01-20 | 2023-01-20 | N/A | 2023-01-20 | N/A | 2023-01-23 | N/A | 2023-04-24 | 2023-04-24 | GOP | 13547.94 | 13547.94 | N/A | 13547.94 | 13547.94 | N/A | N/A | N/A | 2023-01-20 | 2023-01-20 | 2023-01-20 | N/A | 2023-04-24 | completed
| FIRE EXTINGUISHER REFILL | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-02-15 | 2023-01-23 | 2023-02-20 | 2023-03-28 | 2023-03-28 | GOP | 61600 | 61600 | N/A | 58900 | 58900 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-03-28 | completed
| PICHI-PICHI MAKING FOR ARAW NG KABASALAN, (ONE DAY SKILLS DEMONSTRATION) | [19 empty] | JENEBELLE T. CONAHAP | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | 2023-02-13 | N/A | 2023-04-14 | N/A | 2023-02-21 | 2023-02-21 | GOP | 950 | 950 | N/A | 794 | 794 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | 2023-02-21 | completed
| CONSUMABLES FOR COMMUNITY BASED TRAINING IN MARCOTI NG @ R.T. LIM, ZSP | [19 empty] | MAE JANE G. DAGUPAN | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-04-13 | GOP | 1780 | 1780 | N/A | 1460 | 1460 | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-13 | completed
| CONSUMABLES FOR COMMUNITY BASED TRAINING FOR BANANA CHIPS MAKING @R.T. LIM APRIL 13,23 | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 | GOP | 2175 | 2175 | N/A | 2055 | 2055 | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-13 | completed
| CONSUMBLES FOR COMMUNITY BASED TRAINING FOR CAKE DECORATING @ R.T. LIM | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 | GOP | 2540 | 2540 | N/A | 6675 | 6675 | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-11 | 2023-04-13 | completed
| MEALS AND SNACKS FOR THE CONDUCT OF NATIONAL COMPETENCY ASSSESSMENT | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | N/A | 2023-04-11 | N/A | 2023-04-12 | N/A | 2023-04-26 | 2023-04-26 | GOP | 16400 | 16400 | N/A | 16400 | 16400 | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-04-11 | N/A | 2023-04-26 | completed
| MEALS AND SNACKS FOR OFFRICE PERFORMANCE COMMITMENT AND REVIEW (OPCR) VALIDATION | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | 2023-01-05 | N/A | 2023-01-05 | N/A | 2023-01-06 | N/A | 2023-01-09 | 2023-01-09 | GOP | 41000 | 41000 | N/A | 41000 | 41000 | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | 2023-01-05 | N/A | 2023-01-09 | completed
| LAPTOP FOR ADMIN OFFICE (RESIDENT AUDITOR) | [19 empty] | REYMALON C. JUMAWAN | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-05-04 | 2023-05-03 | 2023-05-04 | 2023-05-09 | 2023-05-09 | 2023-05-08 | 2023-05-08 | GOP | 69000 | 69000 | N/A | 70000 | 70000 | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-05-04 | 2023-05-08 | completed
| NATIONAL COMPTENCY ASSESSMENT FOR BPP NC II | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-05-08 | N/A | 2023-05-08 | N/A | 2023-05-09 | N/A | 2023-05-22 | 2023-05-22 | GOP | 19360 | 19360 | N/A | 17052 | 17052 | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-05-08 | N/A | 2023-05-22 | completed
| CONSUMABLES FOR INSTRUCTIONAL DRIVING/TRAINING USE FOR PERIOD OF MARCH 01-15-2023 | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-03-14 | 2023-03-14 | GOP | 10267.7 | 10267.7 | N/A | 10267.7 | 10267.7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | completed
| FUEL CONSUPTION OF ZSPI VEHCLES FOR THE PERIOD OF MARCH 01-15- 23 | [19 empty] | EDUARDO A. PEPINO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-03-16 | 2023-03-16 | GOP | 20791.27 | 20791.27 | N/A | 20791.27 | 20791.27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | completed
| FUEL CONSUPTION (DIESEL & LUBRICANT) USED IN IGP FARMING | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2022-12-12 | 2022-12-12 | GOP | 5158.11 | 5158.11 | N/A | 5158.11 | 5158.11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | completed
| FUEL CONSUPTION OF ZSPI SERVICE VEHICLES FOR THE PERIOD OF MARCH 15-13-2023 | [19 empty] | EDUARDO A. PEPINO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-03-24 | 2023-03-24 | GOP | 19996.01 | 19996.01 | N/A | 19996.01 | 19996.01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | completed
| FUEL/DEISEL CONSUPTION OF ZSPI VEHICLE USE FOR THE PERIOD OF NOVEMBER 16-30,2023 | [19 empty] | GLADYS A. TIONGCO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | N/A | 2023-12-21 | 2023-12-21 | GOP | 13350 | 13350 | N/A | 13350 | 13350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | completed
| FUEL/DEISEL CONSUPTION OF ZSPI VEHICLE USED | [19 empty] | LORETO B. ALAR | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-12-21 | 2023-12-21 | GOP | 49714.57 | 49714.57 | N/A | 49714.57 | 49714.57 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | completed
| FUEL CONSUPTION OF ZSPI VEHCLES FOR THE PERIOD OF FEB. 16-28,2023 | [19 empty] | EDUARDO A. PEPINO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | N/A | 2023-02-27 | 2023-02-27 | GOP | 28314.76 | 28314.76 | N/A | 28314.76 | 28314.76 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | completed
| CONSUMABLES (DIESEL) FOR DRIVING NC II TRAINING | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-02-27 | 2023-02-27 | GOP | 18590.4 | 18590.4 | N/A | 18590.4 | 18590.4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | completed
| FOR USE IN ASSESSMENT | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-18 | N/A | 2023-02-18 | 2023-02-18 | GOP | 6100.5 | 6100.5 | N/A | 2692.77 | 2692.77 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-18 | completed
| FOR USE IN ASSESSMENT | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-03-10 | 2023-03-10 | GOP | 861.6 | 861.6 | N/A | 861.6 | 861.6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | completed
| TRAINING MATERIALS , TOOLS, AND EUQIPMENT FOR PHILIPINE NATIONAL SKILLS COMPETETITION 2023 | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-03-18 | 2023-03-18 | GOP | 49510 | 49510 | N/A | 16540 | 16540 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-18 | completed
| MEALS AND SNACKS FOR TESDA TECHNOLOGY INSTITUTION ADVISORY COUNCIL | [19 empty] | JONH MICHAEL L. MONTILLANO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | N/A | 2023-02-22 | 2023-02-21 | 2023-02-22 | 2023-02-21 | 2023-02-21 | GOP | 4600 | 4600 | N/A | 4600 | 4600 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-21 | completed
| NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NC II JDVP 35 PESFA 25 | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-05-08 | N/A | 2023-05-08 | N/A | 2023-05-06 | N/A | 2023-05-12 | 2023-05-12 | GOP | 16960 | 16960 | N/A | 13959 | 13959 | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-02-22 | 2023-05-12 | completed
| COMMUNITY BASED TRAINING FOR BUKO PIE MAKING ON FEB 22,2023 @ KABASALAN ZSP | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | N/A | 2023-02-13 | N/A | 2023-02-14 | N/A | 2023-02-22 | 2023-02-22 | GOP | 3310 | 3310 | N/A | 2960 | 2960 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-22 | 2023-02-22 | completed
| MEALS AND SNACKS FOR BAC OF BIDS FOR SECURITY SERVICES, MUSICAL INSTRUMENTS, ASSESSEMENT MEDICAL SUPPLIES AND LAPTOP ADMIN OFFICE | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-13 | 2023-04-13 | 2023-04-13 | N/A | 2023-04-13 | N/A | 2023-04-14 | N/A | 2023-04-20 | 2023-04-20 | GOP | 4950 | 4950 | N/A | 4950 | 4950 | N/A | N/A | N/A | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-02-22 | 2023-04-20 | completed
| TRAINING MATERIALS, TOOLS AND EUIPMENT FOR PHILIPPINES NATIONAL SKILLS COMPETITION 2023 | [19 empty] | ORLANDO B. TOMAS | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-14 | 2023-02-08 | 2023-02-14 | 2023-02-15 | 2023-02-17 | 2023-03-18 | 2023-03-18 | GOP | 49510 | 49510 | N/A | 16540 | 16540 | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-22 | 2023-03-18 | completed
| CONSUMABLES FOR COMMUNITY BASED TRAINING IN CHIKN TOCINO (LEADING TO FOOD PROCESSING NCII@ RT.LIM | [19 empty] | EDEN A. MONGCOPA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-06 | 2023-04-18 | 2023-04-06 | 2023-04-07 | 2023-04-07 | 2023-04-13 | 2023-04-13 | GOP | 1180 | 1180 | N/A | 1102 | 1102 | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-06 | 2023-04-13 | completed
| MEALS AND SNACKS FOR THE CONDUCT OF NATIONAL COMPETENCY ASSSESSMENT | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | 2023-02-28 | N/A | 2023-03-01 | N/A | 2023-03-12 | 2023-03-12 | GOP | 12400 | 12400 | N/A | 12400 | 12400 | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-02-28 | N/A | 2023-03-12 | completed
| NATIONAL ASSESSMENT FOR BARTENDING NC II ZSPI DIPLOMA (20 CANDIDATES / AICCATI DIPLOMA | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-12 | 2023-03-12 | GOP | 47939 | 47939 | N/A | 19180 | 19180 | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-12 | completed
| ASSESSMENT MEALS AND SANCKS | [19 empty] | AMY N. MABATID | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | N/A | 2023-01-25 | N/A | 2023-01-26 | N/A | 2023-02-05 | 2023-02-05 | GOP | 17750 | 17750 | N/A | 17750 | 17750 | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | N/A | 2023-02-05 | completed
| COMMUNITY BASED TRAINING FOR TOCINO MAKING ON FEB 22,23 | [19 empty] | UZZEL C. GUERERO | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-14 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GOP | 2395 | 2395 | N/A | 2135 | 2135 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-22 | completed
| COMMUNIITY BASED TRAINING FOR BANANA CHIPS MAKNG ON FEB 22,2023 AT KABASALAN ZSP | [19 empty] | GTRETCHEN J. NUBOG | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-14 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GOP | 1710 | 1710 | N/A | 1028 | 1028 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-22 | completed
| COMMUNIITY BASED TRAINING FOR BANANA CAKE MAKNG ON FEB 22,2023 AT KABASALAN ZSP | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-14 | 2023-02-17 | 2023-02-22 | 2023-02-22 | GOP | 2397 | 2397 | N/A | 2252 | 2252 | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-22 | completed
| CUSTUMES FOR ZSPI DRUM AND LYRE CORPS USE | [19 empty] | EDWIN P, BAYLON | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-04-12 | 12-Aperil-2023 | 2023-04-12 | 2023-04-13 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-18 | 2023-06-19 | 2023-06-19 | GOP | 362400 | 362400 | N/A | 223655 | 223655 | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-04-13 | 2023-06-19 | completed
| TOTAL | [36 empty] | 3504011.36 | 3504011.36 |  | 2020642.78 | 2020642.78
Total Alloted Budget of Procurement Activities | [38 empty] | 3504011.36
Total Contract Price of Procurement Actitvites Conducted | [38 empty] | 2020642.78
Total Savings (Total Alloted Budget - Total Contract Price) | [38 empty] | 1483368.58
0N-GOING PROCUREMENT ACTIVITIES
| CLINIC MEDICINES SUPPLIES AND EQUIPMENNT USE | [19 empty] | MARIE CRIS SOGUE | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-05-29 | 2023-05-26 | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-04 | 2023-06-04 | GOP | 106904.4 | 106904.4 | N/A | 105441 | 105441 | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-05-29 | 2023-06-04 | on-going
| APPLICATION TOOLS, AND EQUIPMENT FOR CSS NCII - COMPLIANCE AUDIT USE | [19 empty] | JOSEPH D. VELASCO | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-29 | 2023-05-15 | 2023-05-16 | 2023-05-19 | 2023-05-19 | 2023-06-19 | 2023-06-19 | GOP | 567100 | 567100 | N/A | 516034 | 516034 | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-29 | 2023-06-19 | on-going
| DEVICE TOOLS AND EQUIPMENT ACCESSORIES FOR CSS TRAINING (BATCH 1) | [19 empty] | JOSEPH D. VELASCO | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-29 | 2023-05-15 | 2023-05-16 | 2023-05-19 | 2023-05-19 | 2023-04-16 | 2023-04-16 | GOP | 107000 | 107000 | N/A | 104340 | 104340 | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-29 | 2023-04-16 | on-going
| MEALS AND SNACKS FOR COA EXIT CONFERENCE USE | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-13 | 2023-03-10 | 2023-03-13 | 2023-03-16 | 2023-03-16 | 2023-03-14 | 2023-03-14 | GOP | 11250 | 11250 | N/A | 11250 | 11250 | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-13 | 2023-03-14 | on-going
| MUSICAL INSTRUMENTS FOR ZSPI DRUM AND LYRE CORPS USE | [19 empty] | EDWIN P. BAYLON | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | 2023-04-24 | 2023-04-20 | 2023-04-24 | 2023-03-16 | 2023-04-27 | 2023-05-16 | 2023-05-16 | GOP | 937500 | 937500 | N/A | 837550 | 837550 | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-04-20 | 2023-04-24 | 2023-05-16 | on-going
| SPARE PARTS AND AND ACCESSORIES FOR SCHOOL VEHICLE CANTER - SEM 402 MAINTENANCE USE | [19 empty] | OSWALDO M. DECHETA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-06-12 | 2023-06-13 | 2023-06-12 | 2023-03-16 | 2023-06-14 | 2023-06-14 | 2023-06-14 | GOP | 1499 | 1499 | N/A | 1279 | 1279 | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-06-12 | 2023-06-14 | on-going
| CONSUMABLES FOR ONE DAY SKILLS TRAINING IN BANANA CHIPS, TOCINO, CHORIZO, PEANUT BUTTER MAKING @CONCEPCION, KABASALAN, ZSP | [19 empty] | JENEBELLE T. CONAHAP | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-03-16 | 2023-05-26 | 2023-05-31 | 2023-05-31 | GOP | 4525 | 4525 | N/A | 4522.25 | 4522.25 | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-31 | on-going
| SNACKS FOR STEP BENEFECIARIES USE | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | 2023-06-16 | N/A | 2023-06-20 | N/A | 2023-06-14 | 2023-06-14 | GOP | 2499 | 2499 | N/A | 2499 | 2499 | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | 2023-06-14 | On-going
| MEALS AND SNACKS FOR ZPPSU GRADUATION CEREMONY 2023 USE | [19 empty] | ROMEE A. TAMSI | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-18 | 2023-06-16 | 2023-06-19 | 2023-06-21 | N/A | 2023-06-18 | 2023-06-18 | GOP | 49149 | 49149 | N/A | 49149 | 49149 | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-18 | 2023-06-18 | On-going
| MATERIALS FOR WATER SUPPLY MAINTENANCE (ADMIN USE) | [19 empty] | ROBERT B. LUNA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-06-19 | 2023-06-21 | 2023-05-22 | 2023-05-26 | 2023-05-26 | GOP | 33000 | 33000 | N/A | 15700 | 15700 | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-17 | 2023-05-26 | On-going
| MATERIALS FOR WATER SUPPLY MAINTENANCE (ADMIN USE) | [19 empty] | ROBERT B. LUNA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-06-19 | 2023-06-21 | 2023-05-22 | 2023-05-26 | 2023-05-26 | GOP | 33000 | 33000 | N/A | 15700 | 15700 | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-17 | 2023-05-26 | On-going
| TOOLS AND EQUIPMENT FOR INSTRUCTIONAL PURPOSES IN BREAD AND PASTRY PRODUCTION NC II AUDIT FINDINGS | [19 empty] | AILEENE A. DACULA | NO | Other Negotiated Procurement (50k or less) | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-06-19 | 2023-02-16 | 2023-02-20 | 2023-05-24 | 2023-05-24 | GOP | 79300 | 79300 | N/A | 78970 | 78970 | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-05-24 | On-going
| C ONTINUATION AND COMPETION OF HOUSEKEEPING NCII NCIII BUILDING | [19 empty] | ROMEE A. TAMSI | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-20 | 2023-02-15 | 2023-02-15 | GOP | 2054395.48 | 2054395.48 | N/A | 1032240.05 | 1032240.05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | On-going
| CONTINUATION AND COMPLETION OF HOSTEL BUILDING- DOMESTIC WORK NCII BUILDING | [19 empty] | ROMEE A. TAMSI | NO | Negotiation (SVP 53.9 above 50k) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-20 | 2023-02-15 | 2023-02-15 | GOP | 4851809.75 | 4851809.75 | N/A | 1034410.16 | 1034410.16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | On-going
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 8838931.63 | 8838931.63 |  | 3809084.46 | 3809084.46
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [9 empty] | APPROVED:
[21 empty] | RAY VIRGIL T. LAGUNAY | [10 empty] | ANALYN J. ELLORIN, Ed.D. | [9 empty] | GLADYS A. TIONGCO, Ed.D.
[21 empty] | BAC Secretariat Member | [10 empty] | BAC Chairperson | [9 empty] | Head of the Procuring Entity
Formulas:
Inspection & Acceptance = [Delivery/ Completion]:AJ72
Inspection & Acceptance = [Delivery/ Completion]
Eligibility Check = [Eligibility Check]
Sub/Open of Bids = [Eligibility Check]
Bid Evaluation = [Eligibility Check]
Post Qual = [Post Qual]
Notice of Award = [Post Qual]