## PMR
Zamboanga Sibugay Polytechnic Institute | [11 empty] | Procurement Monitoring Report as of July 10, 2024
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
310300100001000 | PAKYAW LABOR FOR INSTALATION OF 2 UNITS AICRONDITIONING MACHINE | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | N/A | 2023-08-14 |  | 0 |  | 2023-08-14 | 2023-08-18 | 2023-08-17 | 3 |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 17600 | 17600 |  | 17000 | 17000 |  | 0.034091 | N/A | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | N/A | 2023-08-18 | Completed | FALSE | FALSE
310300100001000 | TARPAULIN, OFFICE SUPPLY, MEALS & SNACKS FOR ZSPI SCHOOL PUBLICATION TRAINING AND WORKSHOP | JOHN MICHAEL L. MOMTILLANO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-11-06 | 2023-11-06 | 2023-11-06 |  | 2012-11-06 | N/A | 2012-11-06 |  |  |  | 2023-11-06 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 | Government of the Philippines (current year's budget) | 500 | 500 |  | 480 | 480 |  |  | N/A | N/A | 2023-11-06 | 2023-11-06 | 2023-11-06 | N/A | 2023-11-07 | Completed
310300100001000 | PAKYAW LABOR FOR MIDCAM STAGE TILE SETTING | ROMEE A. TAMSI | No | NP-53.12 Community Participation | N/A | N/A |  | 2023-12-05 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | N/A | 2023-12-05 |  | 0 |  | 2023-12-05 | 2023-12-05 | 2023-12-05 | 0 |  | 2023-12-25 | 2023-12-25 | Government of the Philippines (current year's budget) | 23120 | 23120 |  | 19410 | 19410 |  | 0.16047 | N/A | N/A | 2023-12-05 | 2023-12-05 | 2023-12-05 | N/A | 2023-12-25 | Completed | FALSE | FALSE
310300100001000 | HIGH SPEED FUEL STATION | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | 2023-02-03 | 2023-02-03 | N/A |  |  | 2023-03-28 | 2023-03-28 | Government of the Philippines (current year's budget) | 4824.96 | 4824.96 |  | 4824.96 | 4824.96 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 3/28/23 | Completed | FALSE | FALSE
310300100001000 | CONSUMJABLES, TOOLS, AND EQUIPMENT FOR REGIONAL SKILLS COMPETION 2023 (RESTAURTANT SERVICES) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-09-13 | 2023-09-13 | 2023-09-13 |  | 2023-09-13 | N/A | 2023-09-13 |  |  |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  | 2023-12-10 | 2023-12-10 | Government of the Philippines (current year's budget) | 388045 | 388045 |  | 6570 | 6570 |  |  | N/A | N/A | 2023-09-13 | 2023-09-13 | 2023-09-13 | N/A | 2023-02-10 | Completed | FALSE | FALSE
310300100001000 | SNACKS FOR ADVISORY COUNCIL MEETING | JOHN MICHAEL L. MOMTILLANO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-10-04 | 2023-10-04 | 2023-10-04 |  | 2023-10-04 | N/A | 2023-10-04 |  | 0 |  | 2023-10-04 | 2023-10-04 | 2023-10-04 | 0 |  | 2023-10-04 | 2023-10-05 | Government of the Philippines (current year's budget) | 2000 | 2000 |  | 2000 | 2000 |  | 0 | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-10-04 | N/A | 2023-10-05 | Completed | FALSE | FALSE
310300100001000 | SUPPLIES, TOOLS, AND EQUIPMENT FOR TILES SETTING AND SCAFFOLD ERECTION NCII USE (DCET III) | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-10-30 | 2023-10-30 | 2023-10-30 |  | 2023-10-30 | N/A | 2023-10-30 |  | 0 |  | 2023-10-31 | 2023-11-03 | 2023-11-03 | 3 |  | 2023-01-22 | 2023-01-22 | Government of the Philippines (current year's budget) | 576310 | 576310 |  | 872178 | 872178 |  | -0.51338 | N/A | N/A | 2023-10-30 | 2023-10-30 | 2023-10-30 | N/A | 2023-01-22 | Completed | FALSE | FALSE
310300100001000 | POLO SHIRT SUBLIMATION, MEALS AND SNACKS FOR REGIONAL SKILLS COMPETITION 2023 | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-10-17 | 2023-10-17 | 2023-10-17 |  | 2023-10-17 | N/A | 2023-10-17 |  |  |  | 2023-10-17 | 2023-10-18 | 2023-10-18 |  |  | 2023-12-10 | 2023-12-10 | Government of the Philippines (current year's budget) | 62500 | 62500 |  | 60000 | 60000 |  |  | N/A | N/A | 2023-10-17 | 2023-10-17 | 2023-10-17 | N/A | 2023-12-10 | Completed
310300100001000 | MEALS AND SNACKS FOR TESDA TECHNOLOGY INSTITUTION ADVISORY COUNCIL 4TH MEETING | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-12-19 | 2023-12-19 | 2023-12-19 |  | 2023-12-19 | N/A | 2023-12-19 |  | 0 |  | 2023-12-19 | 2023-12-19 | 2023-12-19 | 0 |  | 2023-12-23 | 2023-12-23 | Government of the Philippines (current year's budget) | 7500 | 7500 |  | 7500 | 7500 |  | 0 | N/A | N/A | 2023-12-19 | 2023-12-19 | 2023-12-19 | N/A | 2023-12-23 | Completed | FALSE | FALSE
310300100001000 | CONSUMABLES AND MATERIALS FOP ELECTRIC POWER DISTRIBUTION LINE CONSTRUCTION NCII (DEET II) | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-06-30 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | N/A | 2023-06-30 |  | 0 |  | 2023-06-30 | 2023-07-06 | 2023-07-06 | 6 |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 532938 | 532938 |  | 409973 | 409973 |  | 0.23073 | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-06-30 | N/A | 2023-08-30 | Completed | FALSE | FALSE
310300100001000 | EQUIPMENT FOR DMET SMAW UPGRADE | DAN REY A. TAYAG | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | N/A | 2023-09-15 |  | 0 |  | 18/9/23 | 2023-09-21 | 2023-09-21 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 995000 | 995000 |  | 987500 | 987500 |  | 0.0075377 | N/A | N/A | 2023-09-15 | 2023-09-15 | 2023-09-15 | N/A | 2023-09-28 | Completed | FALSE | FALSE
310300100001000 | SUPPLIES, TOOLS, And EQUIPMENT FOR HOUSEKEEPING NCII TRAINING | AILEEN A. CORDOVA | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | 2023-11-21 | 2023-11-21 | 2023-11-21 |  | 2023-11-21 | N/A | 2023-11-21 |  | 0 |  | 2022-11-22 | 2023-11-27 | 2023-11-27 | 370 |  | 2024-02-28 | 2023-02-28 | Government of the Philippines (current year's budget) | 973145 | 973145 |  | 865075 | 865075 |  | 0.11105 | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-11-21 | N/A | 2024-02-23 | Completed | FALSE | FALSE
310300100001000 | SUPPLIES, MATERIALS. & EQUIPMENT FOR PHILIPPINES NATIONAL SKILLS COMPETITION 2024 (ELECTRONICS) | ORLANDO B. TOMAS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-02-15 | 2024-02-15 | 2023-02-15 |  | 2023-02-15 | N/A | 2023-02-15 |  |  |  | 2023-02-15 | 2023-02-15 | 2023-02-15 |  |  | 29-2-23 | 29/2/23 | Government of the Philippines (current year's budget) | 214000 | 214000 |  | 211300 | 211300 |  |  | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-02-15 | N/A | 29/2/23 | Completed
310300100001000 | NATIONAL ASSESSMENT EQUIPMENT, SUPPLIES AND MATERIALS FOR CSS NC II | AMY N. MABATID | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | 2023-11-10 | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | N/A | 2023-11-10 |  |  |  | 2023-11-10 | 2023-11-10 | 2023-11-10 |  |  | 2023-02-07 | 2023-02-07 | Government of the Philippines (current year's budget) | 904644 | 904644 |  | 817590 | 817590 |  |  | N/A | N/A | 2023-11-10 | 2023-11-10 | 2023-11-10 | N/A | 2023-02-07 | Completed
310300100001000 | NATIONAL ASSESSMENT CONSUMABLES FOR NCII BPP-WALK-IN, REGULAR DIPLOMA (65 CANDIDATES) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-02-23 | 23/28/23 | 2023-02-23 |  | 2003-02-23 | N/A | 2023-02-23 |  | 0 |  | 2023-02-26 | 29/2/23 | 29/2/23 |  |  | 2023-03-14 | 2023-03-14 | Government of the Philippines (current year's budget) | 24640 | 24640 |  | 23428 | 23428 |  | 0.049188 | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-02-23 | N/A | 2023-03-14 | Completed | FALSE | FALSE
310300100001000 | TARPAULIN, MATERIALS, MEALS, SNACKS FOR GENDER AND DEVELOPMENT ACTIVITIES/PROGRAM | AILEEN A. CORDOVA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-12-04 | 2023-12-04 | 2023-12-04 |  | 2023-12-04 | N/A | 2023-12-04 |  | 0 |  | 2023-12-04 | 2023-12-06 | 2023-12-05 | 1 |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 15600 | 15600 |  | 15600 | 15600 |  | 0 | N/A | N/A | 2023-12-04 | 2023-12-04 | 2023-12-04 | N/A | 2023-12-07 | Completed | FALSE | FALSE
310300100001000 | EQUIPMENT FOR HR & VSA OFFICE GRAPHIC DESIGNING | MAE JANE G. DAGUPAN | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-09-18 | 2023-09-18 | 2023-09-18 |  | 2023-09-18 | N/A | 2023-09-18 |  | 0 |  | 2023-09-18 | 2023-09-22 | 2023-09-22 | 4 |  | 2024-01-19 | 2024-01-19 | Government of the Philippines (current year's budget) | 164959 | 164959 |  | 136410 | 136410 |  | 0.17307 | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-09-18 | N/A | 2024-01-19 | Completed | FALSE | FALSE
310300100001000 | OFFICE SUPPLIES AND MAINTENANCE FOR BILLING OFFICE | AILEEN A. CORDOVA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | N/A | 2023-07-11 |  | 0 |  | 2023-07-12 | 2023-07-12 | 2023-07-17 | 5 |  | 2023-11-17 | 11-17/23 | Government of the Philippines (current year's budget) | 189642 | 189642 |  | 15000 | 15000 |  | 0.9209 | N/A | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | N/A | 2023-11-17 | Completed | FALSE | FALSE
310300100001000 | CONSUMABLES FOR ADMIN OFFIFCE PHOTOPAPER MACHINE | NASSER H. UTUNGAN | No | Direct Contracting | N/A | N/A |  | 2023-10-23 | 2023-10-23 | 2023-10-23 |  | 2023-10-23 | N/A | 2023-10-23 |  |  |  | N/A | N/A | N/A |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 78722.4 | 78722.4 |  | 78722.4 | 78722.4 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | Completed
310300100001000 | TARPAULIN,OFFICE SUPPLIES, MEALS & SNACKS FOR ZSPI SCHOOL PUBLICATION TRAINING AND WORKSHOP | JOHN MICHAEL L. MOMTILLANO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | N/A | 2023-11-06 |  |  |  | 2023-11-06 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 | Government of the Philippines (current year's budget) | 620 | 620 |  | 612 | 612 |  |  | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | N/A | 2023-11-07 | Completed
310300100001000 | SUPPLIES AND EQUIPMENT FOR DFGDT I-B TRAINING | JUVELYN M. JAUKAL | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | N/A | 2023-11-10 |  |  |  | 2023-11-10 | 2023-11-13 | 2023-11-13 |  |  | 2023-12-15 | 2023-12-15 | Government of the Philippines (current year's budget) | 91299 | 91299 |  | 64110 | 64110 |  |  | N/A | N/A | 2023-11-10 | 2023-11-10 | 2023-11-10 | N/A | 2023-12-15 | Completed
310300100001000 | SUPPLY, DELIVERY AND INSTALLATION OF AIRCONDITIONING UNIT FOR COA OFFICE | ARCELI O. GANZON | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2023-11-13 | 2023-11-13 |  | 2023-11-13 | N/A | 2023-11-13 |  |  |  | 2023-11-14 | 2023-11-17 | 2023-11-17 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 95000 | 95000 |  | 77900 | 77900 |  |  | N/A | N/A | 2023-11-13 | 2023-11-13 | 2023-11-13 | N/A | 2023-12-05 | Completed
310300100001000 | SUPPLIES, MATERIALS, TOOLS AND EQUIPMENT FOR CSS NCII UPGRADE OF TRAINING FACILITY 2023 | JOSEPH D. VELASCO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | N/A | 2023-09-19 |  |  |  | 2023-09-21 | 2023-09-25 | 2023-09-25 |  |  | 2023-12-20 | 2023-12-20 | Government of the Philippines (current year's budget) | 486050 | 486050 |  | 479944 | 479944 |  |  | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-09-19 | N/A | 2023-12-20 | Completed
310300100001000 | DRIVING NC II MSES ASSESSMENT | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 900 | 900 |  | 2488.4 | 2488.4 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-30 | Completed
310300100001000 | NATIONAL ASSESSMENT MATERIALS USED FOR DRIVING NC II | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | N/A | 2023-06-30 |  |  |  | 2023-06-01 | 2023-04-07 | 2023-04-07 |  |  | 2023-05-07 | N/A | Government of the Philippines (current year's budget) | 25500 | 25500 |  | 18000 | 18000 |  |  | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-06-30 | N/A | 2023-07-05 | Completed
310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NCII - 18 CANDIDATES (MALUBAL RT LIM) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-12-13 | 2023-12-13 |  | 2023-12-13 | N/A | 2023-12-13 |  |  |  | 2023-12-14 | 12/17/23 | 12/17/23 |  |  | 12/17/23 | 12/17/23 | Government of the Philippines (current year's budget) | 5060 | 5060 |  | 4889 | 4889 |  |  | N/A | N/A | 2023-12-13 | 2023-12-13 | 2023-12-13 | N/A | 12/17/23 | Completed
310300100001000 | CONSUMABLES FOR CARPENTRY NCII - ASSESSMENT USE (REGUALAR STUDENTS) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2024-02-29 | 2024-02-29 |  | 2024-02-29 | N/A | 2024-02-29 |  |  |  | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  | 2024-03-20 | 2024-03-20 | Government of the Philippines (current year's budget) | 11700 | 11700 |  | 7740 | 7740 |  |  | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-02-29 | N/A | 12/17/24 | Completed
310300100001000 | CONSUMABLES FOR DOLE SKILLS-DEMONSTRATION | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2024-03-14 | 2024-03-14 |  | 2024-03-14 | N/A | 2024-03-14 |  |  |  | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  | 2024-03-15 | 2024-03-15 | Government of the Philippines (current year's budget) | 2060 | 2060 |  | 1754 | 1754 |  |  | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-03-14 | N/A | 2024-03-15 | Completed
310300100001000 | CONSUMABLES FOR THE CONDUCT OF COMMUNITY-BASED TRAINING FOR BUKO PIE MAKING ON MARCH 12,2024 @ BARANGAY TIPAN | CARMIFLOR M. ANDAYA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2024-03-07 | 2024-03-07 |  | 2024-03-07 | N/A | 2024-03-07 |  |  |  | 2024-03-08 | 2024-03-11 | 2024-03-11 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philippines (current year's budget) | 2570 | 2570 |  | 2080.16 | 2080.16 |  |  | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-03-07 | N/A | 2024-03-11 | Completed
310300100001000 | CONSUMABLES FOR THE CONDUCT OF COMMUNITY-BASED TRAINING FOR CHIKEN TOCINO MAKING ON MARCH 12,2024 @BRGY. TIPAN, NAGA, ZSP | MAE JANE G. DAGUPAN | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2024-03-07 | 2024-03-07 |  | 2024-03-07 | N/A | 2024-03-07 |  |  |  | 2024-03-08 | 2024-03-11 | 2024-03-11 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philippines (current year's budget) | 2105 | 2105 |  | 1266.2 | 1266.2 |  |  | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-03-07 | N/A | 2024-03-11 | Completed
310300100001000 | CONSUMABLES FOR THE CONDUCT OF 1 DAY COMMUNITY BASED TRAINING IN BANANA CAKE AND CASSAVA CAKE MAKING AT IMELDA, ZSP | CARMIFLOR M. ANDAYA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-12-13 | 2023-12-13 |  | 2023-12-13 | N/A | 2023-12-13 |  |  |  | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 5990 | 5990 |  | 5961 | 5961 |  |  | N/A | N/A | 2023-12-13 | 2023-12-13 | 2023-12-13 | N/A | 2023-12-13 | Completed
310300100001000 | CLINIC MEDICINES, SUPPLIES AND EQUIPMENT | MARIE CRIS M. SOGUE | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-08-30 | 2023-08-30 |  | 2023-08-30 | N/A | 2023-08-30 |  |  |  | 2023-08-31 | 2023-09-04 | 2023-09-04 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 22064.6 | 22064.6 |  | 21794.5 | 21794.5 |  |  | N/A | N/A | 2023-08-30 | 2023-08-30 | 2023-08-30 | N/A | 2023-09-15 | Completed
310300100001000 | CONSUMABLES, TOOLS AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (BAKERY) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | N/A | 2023-09-15 |  |  |  | 2023-09-15 | 2023-09-21 | 2023-09-21 |  |  | 2023-06-07 | 2023-06-07 | Government of the Philippines (current year's budget) | 36370 | 36370 |  | 36360 | 36360 |  |  | N/A | N/A | 2023-09-15 | 2023-09-15 | 2023-09-15 | N/A | 2023-10-07 | Completed
310300100001000 | TARP AND POLO FOR NATIONAL WOMENS MONTH CELERBRATION | AILEEN A. CORDOVA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2024-03-08 | 2024-03-08 |  | 2024-03-08 | N/A | 2024-03-08 |  |  |  | 2024-03-11 | 2024-03-14 | 2024-03-14 |  |  | 2024-03-15 | 2024-03-15 | Government of the Philippines (current year's budget) | 32980 | 32980 |  | 32960 | 32960 |  |  | N/A | N/A | 2024-03-08 | 2024-03-08 | 2024-03-08 | N/A | 2024-03-15 | Completed
310300100001000 | CONSUMABLES, TOOLS AND EQUIPMENT FOR DCET TRAINING | ROBERTO B. LUNA | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2023-10-31 | 2023-10-31 |  | 2023-10-31 | N/A | 2023-10-31 |  |  |  | 2023-10-31 | 2023-11-03 | 2023-11-03 |  |  | 2024-01-09 | 2024-01-09 | Government of the Philippines (current year's budget) | 100400 | 100400 |  | 58000 | 58000 |  |  | N/A | N/A | 2023-10-31 | 2023-10-31 | 2023-10-31 | N/A | 2023-01-09 | Completed
310300100001000 | TOKEN, TARPAULIN & MEALS AND SNACKS FOR ROTC GRADUATION CEREMONY | EDEN A. MONGCOPA | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | N/A | 2023-05-23 |  |  |  | 2023-05-23 | 2023-05-25 | 2023-05-25 |  |  | 2023-05-24 | 2023-05-24 | Government of the Philippines (current year's budget) | 7500 | 7500 |  | 7500 | 7500 |  |  | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | 2023-05-24 | Completed
310300100001000 | CONSUMABLES FOR EIM- NCII ASSESSMENT USE (CACW-COMPETENCY ASSESSMENT AND CERTIFICATION FOR WORKER) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | N/A | 2023-09-05 |  |  |  | 2023-09-06 | 2023-09-09 | 2023-09-09 |  |  | 2023-11-07 | 2023-11-07 | Government of the Philippines (current year's budget) | 22650 | 22650 |  | 21055 | 21055 |  |  | N/A | N/A | 2023-09-05 | 2023-06-05 | 2023-09-05 | N/A | 2023-11-07 | Completed
310300100001000 | ASSESSMENT OCULAR INSPECTION | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-11-12 | 2023-11-12 |  | 2023-11-12 | 2023-11-12 | 2023-11-12 |  | 2023-11-12 | N/A | 2023-12-12 |  |  |  | 2023-11-13 | 2023-11-16 | 2023-11-16 |  |  | 2023-11-17 | 2023-11-17 | Government of the Philippines (current year's budget) | 3000 | 3000 |  | 3000 | 3000 |  |  | N/A | N/A | 2023-11-12 | 2023-11-12 | 2023-11-12 | N/A | 2023-11-17 | Completed
310300100001000 | CONSUMABLES FOR COMMUNITY BASED TRAINING FOR PANTAWID BENIFICIARIES (LEMON GRASS JUICE) | GRETCHEN J. NUBOG | No | NP-53.9 - Small Value Procurement | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | N/A | 2023-11-17 |  |  |  | 2023-11-17 | 2023-11-20 | 2023-11-20 |  |  | 2023-12-03 | 2023-12-03 | Government of the Philippines (current year's budget) | 25410 | 25410 |  | 24410 | 24410 |  |  | N/A | N/A | 2023-11-17 | 2023-11-17 | 2023-11-17 | N/A | 2023-12-03 | Completed
310300100001000 | COMSUMABLES FOR COMMUNITY BASED TRAINING FOR DSWD (PICHI-PICHI) | JENNEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | N/A | 2023-11-17 |  |  |  | 2023-11-17 | 2023-11-17 | 2023-11-20 |  |  | 2023-12-03 | 2023-12-03 | Government of the Philippines (current year's budget) | 41925 | 41925 |  | 34914 | 34914 |  |  | N/A | N/A | 2023-11-17 | 2023-11-17 | 2023-11-17 | N/A | 2023-12-03 | Completed
310300100001000 | REAPAINTING OF SCRATCHES ON PICK-UP NAVARA PLATE NO. GAN 2367 | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | 2023-11-25 | 2023-11-25 |  | 2023-11-25 | 2023-11-25 | 2023-11-25 |  | 2023-11-25 | N/A | 2023-11-25 |  |  |  | 2023-10-25 | 2024-01-29 | 2024-01-29 |  |  | 2023-03-26 | 2023-03-26 | Government of the Philippines (current year's budget) | 35000 | 35000 |  | 29000 | 29000 |  |  | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-10-25 | N/A | 2024-03-26 | Completed
310300100001000 | CONSUMABLES FOR COMBASED TRAINING JAPANESE CAKE MAKING @ TENAN, IPIL, ZSP | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | N/A | 2023-11-07 |  |  |  | 2023-11-07 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 | Government of the Philippines (current year's budget) | 2320 | 2320 |  | 2002.78 | 2002.78 |  |  | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-11-07 | N/A | 2023-11-07 | Completed
310300100001000 | CONSUMABLES FOR COOKERY NCII ASSESMENT - JDEVP/STII 50 ASSESSEE | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | N/A | 2023-06-30 |  |  |  | 2023-06-30 | 2023-04-07 | 2023-07-04 |  |  | 9/14/23 | 9/14/23 | Government of the Philippines (current year's budget) | 11752 | 11752 |  | 11349 | 11349 |  |  | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-06-30 | N/A | 9/14/23 | Completed
310300100001000 | TOOLS AND EQUIPMENT TO BE USED BY THE ASSESSMENT CENTER FOR ISSURANCE OF E-CERTIFICATE IN ACCORDANCE TESDA CIRCULAR NO. 039S. 2023 | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-10-23 | 2023-10-23 |  | 2023-10-23 | 2023-10-23 | 2023-10-23 |  | 2023-10-23 | N/A | 2023-10-23 |  |  |  | 2023-10-23 | 2023-10-23 | 2023-11-21 |  |  | 2023-11-21 | 2023-11-21 | Government of the Philippines (current year's budget) | 126000 | 126000 |  | 110480 | 110480 |  |  | N/A | N/A | 2023-10-23 | 2023-10-23 | 2023-10-23 | N/A | 2023-11-21 | Completed
310300100001000 | CONSUMABLES FOR COOKERY NC II ASSESSMENT - JDVP/STII- 50 ASSESSEE | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | N/A | 2023-06-30 |  |  |  | 2023-07-01 | 2023-07-04 | 2023-07-04 |  |  | 2023-05-09 | 2023-05-09 | Government of the Philippines (current year's budget) | 19508 | 19508 |  | 19059 | 19059 |  |  | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-06-30 | N/A | 2023-05-09 | Completed
310300100001000 | FOR ASSESSMENT USE | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-08-18 | N/A |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 1626.8 | 1626.8 |  | 1626.8 | 1626.8 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | Completed
310300100001000 | FOR ZSPI ASSESSMENT | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-07-28 | N/A |  |  | 2023-07-28 | 2023-07-28 | Government of the Philippines (current year's budget) | 1626.8 | 1626.8 |  | 1626.8 | 1626.8 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | Completed
310300100001000 | FOR ZSPI ASSESSMENT | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-08-07 | N/A |  |  | 2023-07-08 | 2023-07-08 | Government of the Philippines (current year's budget) | 3446.4 | 3446.4 |  | 3446.4 | 3446.4 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-08 | Completed
310300100001000 | FOR OFFICE SUPPLIES - ASSESSMENT CENTER (1ST AND 2ND QUARTER) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-11 | 2023-07-11 | 2023-11-17 |  |  | 2023-07-09 | 2023-07-09 | Government of the Philippines (current year's budget) | 101500 | 101500 |  | 79555 | 79555 |  |  | N/A | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | N/A | 2023-07-09 | Completed
310300100001000 | TOOLS AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (FRONT OFFICE SERVICES | BRENDA T. JAMBARO | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-09 | 2023-10-09 |  |  |  | 2023-10-09 | 2023-10-13 | 2023-10-13 |  |  | 2023-10-10 | 2023-10-18 | Government of the Philippines (current year's budget) | 91000 | 91000 |  | 87800 | 87800 |  |  | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-10-09 | N/A | 2023-10-18 | Completed
310300100001000 | CONSUMABLES FOR ZSPI GROUND MAINTENANCE (GRASSCUTTER USE) AND GENERATOR | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-10-12 | N/A |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 2700 | 2700 |  | 10194.6 | 10194.6 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | Completed
310300100001000 | CONSUMABLES FOR ZSPI GROUND MAINTENANCE (GRASSCUTTER USE) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-10-25 | N/A |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 2400 | 2400 |  | 3542.3 | 3542.3 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | Completed
310300100001000 | CONSUMABLES FOR INSTIUTIONAL USE AND ASSESSMENT IN DRIVING NC II | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-10-06 | N/A |  |  | 2023-10-06 | 2023-10-06 | Government of the Philippines (current year's budget) | 6800 | 6800 |  | 15560.85 | 15560.85 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | Completed
310300100001000 | MEALS AND SNACKS FOR COA ENTRANCE CONFERENCE AND 4TH MANAGEMENT COMMITTEE (MANCOM) MEETING | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  |  |  | N/A | 2023-10-13 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 | Government of the Philippines (current year's budget) | 33750 | 33750 |  | 33750 | 33750 |  |  | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | 2023-10-16 | Completed
310300100001000 | FOR ZSPI SCHOOL VEHICLE USE | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-10-13 | N/A |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 15719.03 | 15719.03 |  | 15719.03 | 15719.03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | Completed
310300100001000 | MEALS FOR TEACHERS'S DAY CELEBRATION | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-10-04 | 2023-10-04 |  | 2023-10-04 | 2023-10-04 | 2023-10-04 |  | 2023-10-04 | 2023-10-04 | 2023-10-04 |  |  |  | 2023-10-04 | 2023-10-04 | 2023-10-05 |  |  | 2023-10-06 | 2023-10-06 | Government of the Philippines (current year's budget) | 30000 | 30000 |  | 30000 | 30000 |  |  | N/A | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-06 | Completed
310300100001000 | FOR ZSPI SCHOOL VEHICLE USE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-10-23 | N/A |  |  | N/A | 2023-10-23 | Government of the Philippines (current year's budget) | 559.04 | 559.04 |  | 559.04 | 559.04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | Completed
310300100001000 | CONSUMABLES FOR TESDA R.O. & PTC SERVICES VEHICLE | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-10-12 | N/A |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 2250 | 2250 |  | 13193.68 | 13193.68 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | Completed
310300100001000 | CONSUMABLES FOR COM-BASED TRAINING (TENAN, IPIL) LEMON JUICE | GRETCHEN J. NUBOG | No | NP-53.9 - Small Value Procurement | 2023-10-31 | 2023-10-31 |  | 2023-10-31 | 2023-10-31 | 2023-10-31 |  | 2023-10-31 | 2023-10-31 | 2023-10-31 |  |  |  | 2023-10-31 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-03 | 2023-11-03 | Government of the Philippines (current year's budget) | 2805 | 2805 |  | 2800 | 2800 |  |  | N/A | 31/11/23 | 31/11/23 | 31/11/23 | 31/11/23 | 31/11/23 | 2023-03-11 | Completed
310300100001000 | CONSUMABLES FOR COM-BASED TRAINING (TENAN, IPIL) BANANA CAKE MAKING | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-10-31 | 2023-10-31 |  | 2023-10-31 | 2023-10-31 | 2023-10-31 |  | 2023-10-31 | 2023-10-31 | 2023-10-31 |  |  |  | 2023-10-31 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-03 | 2023-11-03 | Government of the Philippines (current year's budget) | 1900 | 1900 |  | 1900 | 1900 |  |  | N/A | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | Completed
310300100001000 | CONSUMABLES FOR THE CAPABILITY BUILDING PROGRAM FOR PROSPECTIVE REGIONAL LEAD ASSESSOR (RLA) IN FBS NC II | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-11-13 | 2023-11-13 |  | 2023-11-13 | 2023-11-13 | 2023-11-13 |  | 2023-11-13 | 2023-11-13 | 2023-11-13 |  |  |  | 2023-11-14 | 2023-11-17 | 2023-11-17 |  |  | 2023-11-17 | 2023-11-17 | Government of the Philippines (current year's budget) | 10335 | 10335 |  | 7732 | 7732 |  |  | N/A | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-17 | Completed
310300100001000 | CONSUMABLES FOR INSTRUCTIONAL USE AND ASSESSMENT INJ DRIVING NCII | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-11-09 | N/A |  |  | 2023-11-10 | 2023-11-10 | Government of the Philippines (current year's budget) | 3600 | 3600 |  | 8182.2 | 8182.2 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | Completed
310300100001000 | FOR ZSPI SCHOOL VEHICLE USE | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-11-14 | N/A |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 172900 | 172900 |  | 144400 | 144400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | Completed
310300100001000 | CONSUMABLES AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (WELDING) | DAN REY A. TAYAG | No | NP-53.9 - Small Value Procurement | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  |  | 2023-09-14 | 2023-09-18 | 2023-09-14 |  |  | 2023-11-03 | 2023-11-03 | Government of the Philippines (current year's budget) | 435900 | 435900 |  | 354930 | 354930 |  |  | N/A | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | N/A | 2023-11-03 | Completed
310300100001000 | CONSUMABLES FOR COMMUNITY-BASED TRAINING PROGRAM @ IPIL HEIGHTS, IPIL, ZSP (ICED COFFEE) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  |  |  | 2023-09-26 | 2023-09-28 | 2023-09-26 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 20045 | 20045 |  | 19830 | 19830 |  |  | N/A | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | N/A | 2023-09-29 | Completed
310300100001000 | OFFICE SUPPLIES AND EQUIPMENT FOR ACCOUNTING AND BUDGET OFFICE - 1ST AND 2ND QUARTER | RONEYRICK JOHN D. ELLOREG | No | NP-53.9 - Small Value Procurement | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-19 | 2023-09-19 |  |  |  | 2023-09-19 | 2023-09-25 | 2023-09-25 |  |  | 2023-11-13 | 2023-11-13 | Government of the Philippines (current year's budget) | 357880 | 357880 |  | 191760 | 191760 |  |  | N/A | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-19 | N/A | 2023-11-13 | Completed
310300100001000 | OFFICE SUPPLIES REGISTRAR'S OFFICE | VERONICA A. RASONABLE | No | NP-53.9 - Small Value Procurement | 2023-09-20 | 2023-09-20 |  | 2023-09-20 | 2023-09-20 | 2023-09-20 |  | 2023-09-20 | 2023-09-20 | 2023-09-20 |  |  |  | 2023-09-21 | 2023-09-25 | 2023-09-25 |  |  | 2023-10-11 | 2023-10-11 | Government of the Philippines (current year's budget) | 293670 | 293670 |  | 251070 | 251070 |  |  | N/A | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | N/A | 2023-10-11 | Completed
310300100001000 | CONSUMABLES,TOOLS, & EQUIPMENT FOR TAILORING NC II AND ROOM MAINTENANCE | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  |  |  | 2023-09-26 | 2023-09-29 | 2023-09-29 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 306094 | 306094 |  | 300630 | 300630 |  |  | N/A | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | N/A | 2023-11-29 | Completed
310300100001000 | CONSUMABLES FOR DRIVING & MASONRY NC I & NC II | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-09-08 | N/A |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 35369 | 35369 |  | 35369 | 35369 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | Completed
310300100001000 | CONSUMABLES, TOOLS, & EQUIPMENT FOR TAILORING NCII AND ROOM MAINTENANCE | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  |  |  | 2023-09-26 | 2023-09-29 | 2023-09-29 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 78610 | 78610 |  | 69000 | 69000 |  |  | N/A | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-11-06 | Completed
310300100001000 | CONSUMABLES FOR IGP GARMENTS | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  | 2023-09-15 | 2023-09-21 | 2023-09-18 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 35600 | 35600 |  | 34276 | 34276 |  |  | N/A | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-11-06 | Completed
310300100001000 | FOR ZSPI SCHOOL VEHICLE USE | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-09-15 | N/A |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 17594.73 | 17594.73 |  | 17594.73 | 17594.73 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | Completed
310300100001000 | CONSUMABLES FOR ZSPI GROUND MAINTENANCE (GRASS CUTTER USE) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-09-29 | N/A |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 1626.8 | 1626.8 |  | 1626.8 | 1626.8 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | Completed
310300100001000 | MATERIALS AND PAKYAW LABOR FOR DEEPWELL CONCRETING/WATER SUPPLY MAINTENANCE | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 |  |  |  | 2023-08-08 | 2023-08-11 | 2023-08-11 |  |  | 2023-08-11 | 2023-08-11 | Government of the Philippines (current year's budget) | 32400 | 32400 |  | 23374 | 23374 |  |  | N/A | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-11 | Completed
310300100001000 | OFFICE EQUIPMENT FOR DRIVING NC II | RICKY O. DAG-UMAN | No | NP-53.9 - Small Value Procurement | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  | 2023-09-15 | 2023-09-18 | 2023-09-18 |  |  | 2023-10-02 | 2023-10-02 | Government of the Philippines (current year's budget) | 42000 | 42000 |  | 35000 | 35000 |  |  | N/A | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-10-02 | Completed
310300100001000 | MATERIALS FOR IMPROVEMENT OF MIDCAM STAGE (TILEWORKS) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-10-05 | 2023-10-05 |  | 2023-10-05 | 2023-10-05 | 2023-10-05 |  | 2023-10-05 | 2023-10-05 | 2023-10-05 |  |  |  | 2023-10-05 | 2023-10-06 | 2023-10-06 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 49940 | 49940 |  | 47398 | 47398 |  |  | N/A | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-12 | Completed
310300100001000 | SUPPLIES AND TOOLS REGIONAL SKILLS COMPETITION SKILLS COMPETITION 2023 (CARPENTRY) | ASIRA B. AMIL | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-09 | 2023-10-09 |  |  |  | 2023-10-10 | 2023-10-13 | 2023-10-13 |  |  | 2023-10-16 | 2023-10-16 | Government of the Philippines (current year's budget) | 199198 | 199198 |  | 197938 | 197938 |  |  | N/A | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-16 | Completed
310300100001000 | OFFICE EQUIPMENT FOR MEALS AND ENGENEERING SECTOR (MACHINE) | RONALDO J. SIASON | No | NP-53.9 - Small Value Procurement | 2023-09-22 | 2023-09-22 |  | 2023-09-22 | 2023-09-22 | 2023-09-22 |  | 2023-09-22 | 2023-09-22 | 2023-09-22 |  |  |  | 2023-09-29 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 34500 | 34500 |  | 23000 | 23000 |  |  | N/A | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-10-24 | Completed
310300100001000 | CONSUMABLES FOR GENERATOR | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-03-24 | N/A |  |  | 2023-03-24 | 2023-03-24 | Government of the Philippines (current year's budget) | 5388.35 | 5388.35 |  | 5388.35 | 5388.35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | Completed
310300100001000 | CONSUMABLES FOR ZSPI GROUND MAINTENANCE F(GRASSCUTTER USE) | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-09-12 | N/A |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 4473.7 | 4473.7 |  | 4473.7 | 4473.7 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | Completed
310300100001000 | FOR SCHOOL VEHICLE SERVICE WITH PLATE NO. GAN 2367 | PESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-11-28 | N/A |  |  | 2023-11-28 | 2023-11-28 | Government of the Philippines (current year's budget) | 7735.44 | 7735.44 |  | 7735.44 | 7735.44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | Completed
310300100001000 | FOR OFFICE SUPPLIES (2ND QUARTER- ADMIN | DAN REY A. TAYAG | No | NP-53.9 - Small Value Procurement | 2022-10-10 | 2002-10-10 |  | 2022-10-10 | 2022-10-10 | 2022-10-10 |  | 2022-10-10 | 2022-10-10 | 2022-10-10 |  |  |  | 2022-10-10 | 2022-10-10 | 2022-10-10 |  |  | 2022-10-17 | 2022-10-17 | Government of the Philippines (current year's budget) | 17600 | 17600 |  | 17600 | 17600 |  |  | N/A | 2022-07-26 | 2022-07-26 | 2022-07-26 | 2022-07-26 | 2022-07-26 | 2022-10-17 | Completed
310300100001000 | OFFICE EQUIPMENT AND SUPPLIES FOR TRAINING INSTRUCTIONAL MATERIALS | JHON MICHAEL L. MONTILLANO | No | NP-53.9 - Small Value Procurement | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  |  |  | 2023-10-12 | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 41800 | 41800 |  | 39500 | 39500 |  |  | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-24 | Completed
310300100001000 | CONSUMABLES FOR REGIONAL SKILLS COMPETITON WATER SYSTEM | ROBERTO B. LUNA | No | NP-53.9 - Small Value Procurement | 2023-10-13 | 2023-10-13 |  | 2023-10-13 | 2023-10-13 | 2023-10-13 |  | 2023-10-13 | 2023-10-13 | 2023-10-13 |  |  |  | 2023-10-13 | 2023-10-13 | 2023-10-13 |  |  | 2023-10-26 | 2023-10-26 | Government of the Philippines (current year's budget) | 27950 | 27950 |  | 15550 | 15550 |  |  | N/A | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-26 | Completed
310300100001000 | USE FOR REGIONAL YEAR END PERFORMANCE ASSESSMENT CUM CHRISTMAS PARTY IN ZAMBOANGA DEL NORTE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-12-26 | 2023-12-26 |  | 2023-12-26 | 2023-12-26 | 2023-12-26 |  | 2023-12-26 | 2023-12-26 | 2023-12-26 |  |  |  | 2023-12-26 | 2023-12-26 | 2023-12-26 |  |  | 2023-12-27 | 2023-12-27 | Government of the Philippines (current year's budget) | 351850 | 351850 |  | 351360 | 351360 |  |  | N/A | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2023-12-27 | Completed
310300100001000 | CONSUMABLES, TOOLS AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (BAKERY) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  | 2023-09-18 | 2023-09-21 | 2023-09-21 |  |  | 2023-11-08 | 2023-11-08 | Government of the Philippines (current year's budget) | 341089 | 341089 |  | 303960 | 303960 |  |  | N/A | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-11-08 | Completed
310300100001000 | I.T. EQUIPMENTS FOR TESDA REGIONAL OFFICE | JOSEPH D. VELASCO | No | NP-53.9 - Small Value Procurement | 2023-07-19 | 2023-07-19 |  | 2023-07-19 | 2023-07-19 | 2023-07-19 |  | 2023-07-19 | 2023-07-19 | 2023-07-19 |  |  |  | 2023-07-20 | 2023-07-25 | 2023-07-25 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 852437 | 852437 |  | 841800 | 841800 |  |  | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-11-06 | Completed
310300100001000 | MATERIALS FOR SCHOOL REPAIR AND MAINTENANCE 2ND QUARTER | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-07-21 | 2023-07-21 |  | 2023-07-21 | 2023-07-21 | 2023-07-21 |  | 2023-07-21 | 2023-07-21 | 2023-07-21 |  |  |  | 2023-07-24 | 2023-07-27 | 2023-07-27 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 11500 | 11500 |  | 11500 | 11500 |  |  | N/A | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-09-18 | Completed
310300100001000 | CONSUMABLES FOR VEHICLE MAINTENANCE (CANTER SEM 402) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 |  |  |  | 2023-08-08 | 2023-08-14 | 2023-08-14 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 34000 | 34000 |  | 31200 | 31200 |  |  | N/A | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-16 | Completed
310300100001000 | CONSUMABLES FOR 1 DAY COMMUNITY-BASED TRAINING FOR BUKO PIE AND BANANA CAKE MAKING @ IMELDA ZSP | GRETCHEN J. NUBOG | No | NP-53.9 - Small Value Procurement | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  |  |  | 2023-09-08 | 2023-09-11 | 2023-09-08 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 9489 | 9489 |  | 9212 | 9212 |  |  | N/A | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-11 | Completed
310300100001000 | CONSUMABLES FOR PLUMBING NC I COMABASED TRAINING (OLUTANGA,ZSP) | PHILIP D. TRAYVILLA | No | NP-53.9 - Small Value Procurement | 2023-08-19 | 2023-08-19 |  | 2023-08-19 | 2023-08-19 | 2023-08-19 |  | 2023-08-19 | 2023-08-19 | 2023-08-19 |  |  |  | 2023-09-20 | 2023-09-25 | 2023-09-25 |  |  | 2023-10-16 | 2023-10-16 | Government of the Philippines (current year's budget) | 73600 | 73600 |  | 56650 | 56650 |  |  | N/A | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-10-16 | Completed
310300100001000 | CONSUMABLES SKILLS DEMONSTRATION SKILLS DEMONSTRATION THIS COMING FOUNDATION DAY (JAPANESE CAKE MAKING) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  | 2023-09-15 | 2023-09-18 | 2023-09-15 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 12420 | 12420 |  | 11829 | 11829 |  |  | N/A | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-18 | Completed
310300100001000 | TOOLS AND EQUIPMENT FOR INSTRUCTIONAL PURPOSE IN BREAD AND PASTRY PRODUCTION NCII AUDIT FINDINGS | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-02-14 | 2023-02-14 |  | 2023-02-14 | 2023-02-14 | 2023-02-14 |  | 2023-02-14 | 2023-02-14 | 2023-02-14 |  |  |  | 2023-02-15 | 2023-02-20 | 2023-02-20 |  |  | 2023-05-24 | 2023-05-24 | Government of the Philippines (current year's budget) | 79300 | 79300 |  | 78970 | 78970 |  |  | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-05-24 | Completed
310300100001000 | FOR OFFICE SUPPLIES ASSESSMENT (3RD AND 4TH QUARTER) & REPLACEMENT OF CCTV PARTS (DAMAGE) AND MAINTENANCE FOR ASSESSMENT | AMY N. MABATID | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-02-14 | 2023-02-14 |  | 2023-02-14 | 2023-02-14 | 2023-02-14 |  | 2023-02-14 | 2023-02-14 | 2023-02-14 |  |  |  | 2023-02-15 | 2023-02-20 | 2023-02-20 |  |  | 2023-05-24 | 2023-05-24 | Government of the Philippines (current year's budget) | 173490 | 173490 |  | 83625 | 83625 |  |  | N/A | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-05-24 | Completed
310300100001000 | ASSESSMENT MEALS AND SNACKS | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-27 | 2023-08-27 |  | 2023-08-27 | 2023-08-27 | 2023-08-27 |  | 2023-08-27 | 2023-08-27 | 2023-08-27 |  |  |  | 2023-08-28 | 2023-08-31 | 2023-08-31 |  |  | 2023-09-05 | 2023-09-05 | Government of the Philippines (current year's budget) | 16100 | 16100 |  | 16100 | 16100 |  |  | N/A | 2023-08-27 | 2023-08-27 | 2023-08-27 | 2023-08-27 | 2023-08-27 | 2023-09-05 | Completed
310300100001000 | FOR SCHOOL REPAIR AND MAINTENANCE USE | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | 2022-09-12 | 2022-09-12 |  | 2022-09-12 | 2022-09-12 | 2022-09-12 |  | 2022-09-12 | 2022-09-12 | 2022-09-12 |  |  |  | 2023-09-12 | 2023-02-02 | 2023-02-02 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 62000 | 62000 |  | 31320 | 31320 |  |  | N/A | 2022-09-12 | 2022-09-12 | 2022-09-12 | 2022-09-12 | 2022-09-12 | 2023-08-15 | Completed
310300100001000 | FOR OFFICE SUPPLIES (3RD QUARTER) ADMIN | LYNDRE G. BAYOTAS | No | NP-53.9 - Small Value Procurement | 2023-03-16 | 2023-03-16 |  | 2023-03-16 | 2023-03-16 | 2023-03-16 |  | 2023-03-16 | 2023-03-16 | 2023-03-16 |  |  |  | 2023-03-20 | 2023-03-20 | 2023-03-22 |  |  | 2023-07-14 | 2023-07-14 | Government of the Philippines (current year's budget) | 92100 | 92100 |  | 66660 | 66660 |  |  | N/A | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-07-14 | Completed
310300100001000 | MEALS AND SNACKS FOR COA EXIT CONFERENCE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-03-10 | 2023-03-10 |  | 2023-03-10 | 2023-03-10 | 2023-03-10 |  | 2023-03-10 | 2023-03-10 | 2023-03-10 |  |  |  | 2023-03-16 | 2023-03-16 | 2023-03-16 |  |  | 2023-03-14 | 2024-03-14 | Government of the Philippines (current year's budget) | 11250 | 11250 |  | 11250 | 11250 |  |  | N/A | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-14 | Completed
310300100001000 | SNACKS FOR ZSPI STAR APPLICATION ORREIENTATION | ANALYN J. ELLORIN | No | NP-53.9 - Small Value Procurement | 2023-04-03 | 2023-04-03 |  | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-04-03 | 2023-04-03 | 2023-04-03 |  |  |  | 2023-04-03 | 2023-04-03 | 2023-04-03 |  |  | 2023-04-04 | 2023-04-04 | Government of the Philippines (current year's budget) | 1600 | 1600 |  | 1600 | 1600 |  |  | N/A | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-04 | Completed
310300100001000 | FOR MSES ASSESSMENT | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-04-15 | N/A |  |  | 2023-04-15 | 2023-04-15 | Government of the Philippines (current year's budget) | 2440.2 | 2440.2 |  | 2440 | 2440 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-15 | Completed
310300100001000 | NATIONAL COMPETENCY ASSESSEMENT CONSUMABLES FOR EIM NCII (INDUSTRIAL WORKER & JDP) 40 CANDIDATES | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 09/05/20230 | 2023-05-09 |  | 2023-05-09 | 2023-05-09 | 2023-05-09 |  | 2023-05-09 | 2023-05-09 | 2023-05-09 |  |  |  | 2023-05-09 | 2023-05-09 | 2023-05-09 |  |  | 2023-06-19 | 2023-06-19 | Government of the Philippines (current year's budget) | 36300 | 36300 |  | 28045 | 28045 |  |  | N/A | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-06-19 | Completed
310300100001000 | KITCHEN UTENSILS FOR ZSPI CATERING SERVICES (INCOME GENERATING PROJECT) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-03-29 | 2023-03-29 |  | 2023-03-29 | 2023-03-29 | 2023-03-29 |  | 2023-03-29 | 2023-03-29 | 2023-03-29 |  |  |  | 2023-03-29 | 2023-05-31 | 2023-05-31 |  |  | 2023-06-02 | 2023-06-02 | Government of the Philippines (current year's budget) | 48000 | 48000 |  | 39200 | 39200 |  |  | N/A | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-06-02 | Completed
310300100001000 | CONSUMABLES FOR ONE DAY SKILLS TRAINING IN BANANA CHIPS, TOCINO MAKING, CHORIZO MAKING, PEANUT BUTTER MAKING @ CONCEPCION, KABASALAN, ZSP | JENNEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | 2023-05-23 | 2023-05-23 |  |  |  | 2023-05-23 | 2023-05-26 | 2023-05-26 |  |  | 2023-05-26 | 2023-05-26 | Government of the Philippines (current year's budget) | 4525 | 4525 |  | 4522 | 4522 |  |  | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-26 | Completed
310300100001000 | PAKYAW LABOR FOR ADMIN OFFICE SOFA COVER REPAIR | GLADYS A. TIONGCO, Ed.D. | No | NP-53.9 - Small Value Procurement | 2023-05-22 | 2023-05-22 |  | 2023-05-22 | 2023-05-22 | 2023-05-22 |  | 2023-05-22 | 2023-05-22 | 2023-05-22 |  |  |  | 2023-05-23 | 2023-05-26 | 2023-05-26 |  |  | 2023-05-30 | 2023-05-30 | Government of the Philippines (current year's budget) | 10000 | 10000 |  | 9500 | 9500 |  |  | N/A | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-30 | Completed
310300100001000 | CONSUMABLES FOR ASSESSMENT DRIVING NC II AND AUTOMOTIVE SERVICING NC I | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-05-12 | N/A |  |  | 2023-05-12 | 2023-05-12 | Government of the Philippines (current year's budget) | 3350 | 3350 |  | 3350 | 3350 |  |  | N/A | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-12 | Completed
310300100001000 | APPLICATION, TOOLS, AND EQUIPMENT FOR CSS NC II- COMPLIANCE AUDIT | JOSEPH D. VELASCO | No | NP-53.9 - Small Value Procurement | 2023-05-15 | 2023-05-15 |  | 2023-05-15 | 2023-05-15 | 2023-05-15 |  | 2023-05-15 | 2023-05-15 | 2023-05-15 |  |  |  | 2023-05-16 | 2023-05-19 | 2023-05-19 |  |  | 2023-06-19 | 2023-06-19 | Government of the Philippines (current year's budget) | 567100 | 567100 |  | 516034 | 516034 |  |  | N/A | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-06-19 | Completed
310300100001000 | SPARE PARTS FOR RISO MACHINE MAINTENANCE | NASSER H. UTUNGAN | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-05-19 | N/A |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 42147.13 | 42147.13 |  | 42147.13 | 42147.13 |  |  | N/A | M | N/A | N/A | N/A | N/A | 2023-09-14 | Completed
310300100001000 | CONSUMABLES FOR AGRICULTURE CROP PRODUCTION NC II ASSESSMENT USE (JDVP) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-16 | 2023-06-16 |  | 2023-06-16 | 2023-06-16 | 2023-06-16 |  | 2023-06-16 | 2023-06-16 | 2023-06-16 |  |  |  | 2023-06-15 | 2023-06-18 | 2023-06-18 |  |  | 2023-07-18 | 2023-07-18 | Government of the Philippines (current year's budget) | 29570 | 29570 |  | 21390 | 21390 |  |  | N/A | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-07-18 | Completed
310300100001000 | NATIONAL COMPETENCY ASSESSMEMENT CONSUMABLES FOR EIM- NCII (REGULAR TARINEES - ZAMSURECO II) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-10 | 2023-06-10 |  | 2023-06-10 | 2023-06-10 | 2023-06-10 |  | 2023-06-10 | 2023-06-10 | 2023-06-10 |  |  |  | 2023-06-13 | 2023-06-14 | 2023-06-14 |  |  | 2023-06-19 | 2023-06-19 | Government of the Philippines (current year's budget) | 49900 | 49900 |  | 43394 | 43394 |  |  | N/A | 2023-06-10 | 2023-06-10 | 2023-06-10 | 2023-06-10 | 2023-06-10 | 2023-06-19 | Completed
310300100001000 | CONSUMABLES FOR AGRICULTURE CROP PRODUCTION NC II ASSESSMENT USE (SCHOLAR) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-15 | 2023-06-15 |  | 2023-06-15 | 2023-06-15 | 2023-06-15 |  | 2023-06-15 | 2023-06-15 | 2023-06-15 |  |  |  | 2023-06-16 | 2023-06-20 | 2023-06-20 |  |  | 2023-07-27 | 2023-07-27 | Government of the Philippines (current year's budget) | 29570 | 29570 |  | 21390 | 21390 |  |  | N/A | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-07-27 | Completed
310300100001000 | SPORTS EQUIPMENT FOR TESDA ZAMPEN FRIENDSHIP GAME 2023 & PHYSICAL EDUCATION INSTRUCTIONAL PURPOSE | JEREMY-KARL K. ALAGON | No | NP-53.9 - Small Value Procurement | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  | 2023-08-10 | 2023-08-14 | 2023-08-10 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 215560 | 215560 |  | 214137 | 214137 |  |  | N/A | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-15 | Completed
310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NCII - JDVP/ SENIOR HIGH SCHOOL | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 2023-06-28 | 2023-06-28 |  |  |  | 2023-06-28 | 2023-06-30 | 2023-06-30 |  |  | 2023-08-04 | 2023-08-04 | Government of the Philippines (current year's budget) | 18410 | 18410 |  | 16130 | 16130 |  |  | N/A | 2023-06-28 | 2023-06-28 | 2023-06-28 | 2023-06-28 | 2023-06-28 | 2023-08-04 | Completed
310300100001000 | BOOKS FOR ZSPI LIBRARY | JOSEPHINE Z. BACUDAN | No | NP-53.9 - Small Value Procurement | 2023-05-26 | 2023-05-26 |  | 2023-05-26 | 2023-05-26 | 2023-05-26 |  | 2023-05-26 | 2023-05-26 | 2023-05-26 |  |  |  | 2023-05-29 | 2023-06-01 | 2023-06-01 |  |  | 2023-02-26 | 2023-02-26 | Government of the Philippines (current year's budget) | 526875 | 526875 |  | 522580 | 522580 |  |  | N/A | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-06-26 | Completed
310300100001000 | SNACKS FOR STEP BENEFECIARIES | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-06-07 | 2023-06-07 |  | 2023-06-07 | 2023-06-07 | 2023-06-07 |  | 2023-06-07 | 2023-06-07 | 2023-06-07 |  |  |  | 2023-06-08 | 2023-07-13 | 2023-06-13 |  |  | 2023-06-14 | 2023-06-14 | Government of the Philippines (current year's budget) | 2500 | 2500 |  | 2500 | 2500 |  |  | N/A | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-14 | Completed
310300100001000 | CONSUMABLES FOR FBS NCIII TRAINING (DIPLOMA IN HOSPITALITY AND MANAGEMENT TECHNOLOGY II AND DIPLOMA IN FOOD PRODUCTION AND MANAGEMENT TECHNOLOGY | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-17 | 2023-07-11 |  |  | 2023-08-03 | 2023-08-03 | Government of the Philippines (current year's budget) | 479890 | 479890 |  | 435565 | 435565 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-08-03 | Completed
310300100001000 | CONSUMABLES FOR FBS NCIII TRAINING (DIPLOMA IN HOSPITALITY AND MANAGEMENT TECHNOLOGY II AND DIPLOMA IN FOOD PRODUCTION AND MANAGEMENT TECHNOLOGY | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-11 | 2023-07-17 |  |  | 2023-09-08 | 2023-09-08 | Government of the Philippines (current year's budget) | 168400 | 168400 |  | 166400 | 166400 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-08-09 | Completed
310300100001000 | NATIONAL ASSESSMENT USED IN CSS NC II (JDVP/TWSP-100 CANDIDATES) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-15 | 2023-07-15 |  |  | 2023-08-09 | 2023-08-09 | Government of the Philippines (current year's budget) | 26000 | 26000 |  | 17500 | 17500 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-08-09 | Completed
310300100001000 | CONSUMABLES FOR FBS NCIII TRAINING (DIPLOMA IN HOSPITALITY AND MANAGEMENT TECHNOLOGY II AND DIPLOMA IN FOOD PRODUCTION AND MANAGEMENT TECHNOLOGY | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-17 | 2023-07-17 |  |  | 2023-08-11 | 2023-08-11 | Government of the Philippines (current year's budget) | 265000 | 265000 |  | 233750 | 233750 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-08-11 | Completed
310300100001000 | MATERIALS FOR ELEVATION OF WATER OF ELECTRICAL BUILDING | ROBERTO B. LUNA | No | NP-53.9 - Small Value Procurement | 2023-07-05 | 2023-07-05 |  | 2023-07-05 | 2023-07-05 | 2023-07-05 |  | 2023-07-05 | 2023-07-05 | 2023-07-05 |  |  |  | 2023-07-05 | 2023-07-11 | 2023-07-11 |  |  | 2023-07-13 | 2023-07-13 | Government of the Philippines (current year's budget) | 12500 | 12500 |  | 9950 | 9950 |  |  | N/A | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-13 | Completed
310300100001000 | ASSESSMENT CONSUMABLES FOR MASONRY NC II- 25 CANDIDATES (PTC-BUUG) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-15 | 2023-07-15 |  |  | 2023-07-15 | 2023-07-15 | Government of the Philippines (current year's budget) | 20650 | 20650 |  | 17320 | 17320 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-15 | Completed
310300100001000 | ASSESSMENT CONSUMABLES FOR MASONRY NC II- 25 CANDIDATES (RL) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-15 | 2023-07-15 |  |  | 2023-07-15 | 2023-07-15 | Government of the Philippines (current year's budget) | 22700 | 22700 |  | 18940 | 18940 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-15 | Completed
310300100001000 | GRAVELING OF ZSPI PARKING AREA | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-07-10 | 2023-07-10 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 |  |  |  | 2023-07-11 | 2023-07-14 | 2023-07-14 |  |  | 2023-07-14 | 2023-07-14 | Government of the Philippines (current year's budget) | 30000 | 30000 |  | 22060 | 22060 |  |  | N/A | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-14 | Completed
310300100001000 | MATERIALS AND TARPAULIN FOR ZSPI SINAGES | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | 2023-07-12 | 2023-07-12 |  | 2023-07-12 | 2023-07-12 | 2023-07-12 |  | 2023-07-12 | 2023-07-12 | 2023-07-12 |  |  |  | 2023-07-13 | 2023-07-18 | 2023-07-18 |  |  | 2023-07-21 | 2023-07-21 | Government of the Philippines (current year's budget) | 20000 | 20000 |  | 15360 | 15360 |  |  | N/A | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-21
310300100001000 | CONSUMABLES FOR COOKERY MC II ASSSESSMENT - JDVP/STII- 50 ASESSEE | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | 2023-06-30 | 2023-06-30 |  |  |  | 2023-07-01 | 2023-07-04 | 2023-07-04 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 10470 | 10470 |  | 8185 | 8185 |  |  | N/A | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-07 | Completed
310300100001000 | CONSUMBALES, TOOLS, & EQUIPMENT FOR BPP NC II (DFSMT II) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-07-18 | 2023-07-18 |  | 2023-07-18 | 2023-07-18 | 2023-07-18 |  | 2023-07-18 | 2023-07-18 | 2023-07-18 |  |  |  | 2023-07-19 | 2023-07-24 | 2023-07-24 |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 48846 | 48846 |  | 42478 | 42478 |  |  | N/A | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-08-18 | Completed
310300100001000 | OFFICE SUPPLIES, EQUIPMENT, VEHICLE, TOOLS & ROOM MAINTENANCE FOR 1ST AND 2ND QUARTER - ADMIN | LYNDRE G. BAYOTAS | No | NP-53.9 - Small Value Procurement | 2023-07-17 | 2023-07-17 |  | 2023-07-17 | 2023-07-17 | 2023-07-17 |  | 2023-07-17 | 2023-07-17 | 2023-07-17 |  |  |  | 2023-07-18 | 2023-07-21 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 891525 | 891525 |  | 704994 | 704994 |  |  | N/A | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-09-19 | Completed
310300100001000 | SUPPLIES FOR ZSPI CAMPUS - AIRCONDITIONING MAINTNANCE | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | 2023-07-24 | 2023-07-24 |  | 2023-07-24 | 2023-07-24 | 2023-07-24 |  | 2023-07-24 | 2023-07-24 | 2023-07-24 |  |  |  | 2023-07-25 | 2023-07-28 | 2023-07-28 |  |  | 2023-08-17 | 2023-08-17 | Government of the Philippines (current year's budget) | 48300 | 48300 |  | 36920 | 36920 |  |  | N/A | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-08-17 | Completed
310300100001000 | SPARE PARTS FOR GRASSCUTTER TO BE USED IN CAMPUS GROUND MAINTENANCE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 |  |  |  | 2023-07-26 | 2023-07-31 | 2023-07-31 |  |  | 2023-08-11 | 2023-08-11 | Government of the Philippines (current year's budget) | 26000 | 26000 |  | 25050 | 25050 |  |  | N/A | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-08-11 | Completed
310300100001000 | CONSUMABLES FOR PLUMBING NC I COMABASED TRAINING (OLUTANGA,ZSP) | PHILIP D. TRAYVILLA | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 |  |  |  | 2023-07-25 | 2023-07-28 | 2023-07-28 |  |  | 2023-08-03 | 2023-08-03 | Government of the Philippines (current year's budget) | 49850 | 49850 |  | 40205 | 40205 |  |  | N/A | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-03-08 | Completed
310300100001000 | TOOLS FOR CONSUMABLES FOR EIM NC II (COMMUNITY BASED TRAINING- MABUHAY, ZAMBOANGA SIBUGAY) | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | 2023-07-19 | 2023-07-19 |  | 2023-07-19 | 2023-07-19 | 2023-07-19 |  | 2023-07-19 | 2023-07-19 | 2023-07-19 |  |  |  | 2023-07-20 | 2023-07-25 | 2023-07-25 |  |  | 2023-08-17 | 2023-08-17 | Government of the Philippines (current year's budget) | 156825 | 156825 |  | 102230 | 102230 |  |  | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-08-17 | Completed
310300100001000 | CONSUMABLES, TOOLS, & EQUIPMENT FOR BPP NC II (DFPHMT II) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-07-18 | 2023-07-18 |  | 2023-07-18 | 2023-07-18 | 2023-07-18 |  | 2023-07-18 | 2023-07-18 | 2023-07-18 |  |  |  | 2023-07-19 | 2023-07-24 | 2023-07-24 |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 4800 | 4800 |  | 4160 | 4160 |  |  | N/A | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-07-18 | 2023-08-18 | Completed
310300100001000 | COMMERCIAL CHECK FOR CASHIER'S OFFICE | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-07-21 | N/A |  |  | 2023-07-17 | 2023-07-17 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 6000 | 6000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | Completed
310300100001000 | OFFICE SUPPLIE & EQUIPMENT FOR GIDANCE OFFICE | REUBEN P. SAJULGA | No | NP-53.9 - Small Value Procurement | 2023-07-28 | 2023-07-28 |  | 2023-07-28 | 2023-07-28 | 2023-07-28 |  | 2023-07-28 | 2023-07-28 | 2023-07-28 |  |  |  | 2023-07-28 | 2023-07-31 | 2023-07-28 |  |  | 2023-09-21 | 2023-09-21 | Government of the Philippines (current year's budget) | 146000 | 146000 |  | 79752 | 79752 |  |  | N/A | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-09-21 | Completed
310300100001000 | MEALS AND SNACKS FOR THE CONDUCT OF NATIONAL COMPETENCY ASSESSEMENT | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-10 | 2023-07-10 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 |  |  |  | 2023-07-11 | 2023-07-14 | 2023-07-14 |  |  | 2023-07-24 | 2023-07-24 | Government of the Philippines (current year's budget) | 23000 | 23000 |  | 23000 | 23000 |  |  | N/A | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-24 | Completed
310300100001000 | MEALS AND FOR THE CONDUCT OF NATIONAL COMPETENCY ASSESSMENT | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-24 | 2023-07-24 |  | 2023-07-24 | 2023-07-24 | 2023-07-24 |  | 2023-07-24 | 2023-07-24 | 2023-07-24 |  |  |  | 2023-07-28 | 2023-07-28 | 2023-07-28 |  |  | 2023-07-30 | 2023-07-30 | Government of the Philippines (current year's budget) | 4600 | 4600 |  | 4600 | 4600 |  |  | N/A | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-30 | Completed
310300100001000 | SNACKS FOR MENTAL AWARENESS- ZSPI ADMIN | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 |  |  |  | 2023-07-25 | 2023-07-28 | 2023-07-28 |  |  | 2023-07-31 | 2023-07-31 | Government of the Philippines (current year's budget) | 4550 | 4550 |  | 4550 | 4550 |  |  | N/A | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-31 | Completed
310300100001000 | FOR OFFICE SUPPLIES - ASSESSMENT CENTER (1ST AND 2ND QUARTER) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-17 | 2023-07-17 |  |  | 2023-09-02 | 2023-09-02 | Government of the Philippines (current year's budget) | 45950 | 45950 |  | 34790 | 34790 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-09-02 | Completed
310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR PLUMBING NC I STEP (OLUTANGA, ZSPI) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  | 2023-08-09 | 2023-08-14 | 2023-08-14 |  |  | 2023-08-14 | 2023-09-01 | Government of the Philippines (current year's budget) | 20800 | 20800 |  | 18580 | 18580 |  |  | N/A | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-01-09 | Completed
310300100001000 | OFFICE SUPPLIES AND MAINTENANCE FOR BILLING OFFICE | AILEEN A. CORDOVA | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-17 | 2023-07-17 |  |  | 2023-11-16 | 2023-11-16 | Government of the Philippines (current year's budget) | 189642 | 189642 |  | 174607 | 174607 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-11-16 | Completed
310300100001000 | MATERIALS FOR ELECTRICAL LINE SOUREE FOR HOUSEKEEPING NC III BUILDING | RONNEL B. PEPINO | No | NP-53.9 - Small Value Procurement | 2023-07-31 | 2023-07-31 |  | 2023-07-31 | 2023-07-31 | 2023-07-31 |  | 2023-07-31 | 2023-07-31 | 2023-07-31 |  |  |  | 2023-08-01 | 2023-08-06 | 2023-08-06 |  |  | 2023-08-04 | 2023-08-04 | Government of the Philippines (current year's budget) | 25500 | 25500 |  | 17100 | 17100 |  |  | N/A | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-08-04 | Completed
310300100001000 | MATERIALS AND PAKYAW LABOR FOR DEEPWELL CONCRETING/WATER SUPPLY MAINTENANCE | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 |  |  |  | 2023-08-10 | 2023-08-11 | 2023-08-11 |  |  | 2023-08-17 | 2023-08-17 | Government of the Philippines (current year's budget) | 8400 | 8400 |  | 8360 | 8360 |  |  | N/A | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-17 | Completed
310300100001000 | PAKYAW LABOR FOR SEPTIC TANK CLEANER | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  | 2023-08-11 | 2023-08-16 | 2023-08-16 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 40500 | 40500 |  | 37800 | 37800 |  |  | N/A | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-16 | Completed
310300100001000 | FOR GRASS CUTTER USE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-08-14 | N/A |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 4285.75 | 4285.75 |  | 4285.75 | 4285.75 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | Completed
310300100001000 | CONSUMABLES FOR ZAMBOANGA CITY TRADES FAIR DISPLAY | JENNEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2023-08-04 | 2023-08-04 |  | 2023-08-04 | 2023-08-04 | 2023-08-04 |  | 2023-08-04 | 2023-08-04 | 2023-08-04 |  |  |  | 2023-08-04 | 2023-08-07 | 2023-08-07 |  |  | 2023-08-08 | 2023-08-08 | Government of the Philippines (current year's budget) | 15460 | 15460 |  | 15100 | 15100 |  |  | N/A | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-08-08 | Completed
310300100001000 | LED WALL RENTAL, POLO SHIRT SUBLIMATION AND DECORATION MATERIALS FOR ZAMPEN FRIENDSHIP GAMES | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  | 2023-08-14 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 32500 | 32500 |  | 31525 | 31525 |  |  | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-16 | Completed
310300100001000 | MEALS AND SNACKS FOR ZSPI GRADUATION AND CERTIFICATION CEREMONY | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-29 | 2023-08-29 |  | 2023-08-29 | 2023-08-29 | 2023-08-29 |  | 2023-08-29 | 2023-08-29 | 2023-08-29 |  |  |  | 2023-08-29 | 2023-08-29 | 2023-08-29 |  |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 32500 | 32500 |  | 32500 | 32500 |  |  | N/A | 2023-08-29 | 2023-08-29 | 2023-08-29 | 2023-08-29 | 2023-08-29 | 2023-08-30 | Completed
310300100001000 | MEALS AND SNACKS FOR THE TESDA BARANGAY ACCESS TO SKILLS AND SCHOLARSHIP OPPORTUNITIES (BASO) AND TESDA ZAMPEN SERBILIS | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-15 | 2023-08-15 |  | 2023-08-15 | 2023-08-15 | 2023-08-15 |  | 2023-08-15 | 2023-08-15 | 2023-08-15 |  |  |  | 2023-08-16 | 2023-08-16 | 2023-08-16 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 140000 | 140000 |  | 139650 | 139650 |  |  | N/A | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-16 | Completed
310300100001000 | FUNITURE FOR ZSPI INSTRUCTIONAL PURPOSE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-15 | 2023-08-15 |  | 2023-08-15 | 2023-08-15 | 2023-08-15 |  | 2023-08-15 | 2023-08-15 | 2023-08-15 |  |  |  | 2023-08-16 | 2023-07-25 | 2023-08-21 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 960000 | 960000 |  | 708000 | 708000 |  |  | N/A | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-29 | Completed
310300100001000 | MATERIALS, TOOLS AND EQUIPMENT FOR MASONRY NCI BUILDING MAINTENANCE | ROBERTO B. LUNA | No | NP-53.9 - Small Value Procurement | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  | 2023-08-14 | 2023-08-17 | 2023-08-17 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 174275 | 174275 |  | 159985 | 159985 |  |  | N/A | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-10-13 | Completed
310300100001000 | MEALS, SNACKS, TARPAULIN AND MATERIALS FOR ZPPSU- CERTIFICATE OF PROGRAM COMPLIANCE EVALUATION | MA. EVELYN T. TUBAN | No | NP-53.9 - Small Value Procurement | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | 2023-08-01 | 2023-08-01 |  |  |  | 2023-08-01 | 2023-08-04 | 2023-08-04 |  |  | 2023-08-09 | 2023-08-09 | Government of the Philippines (current year's budget) | 47700 | 47700 |  | 46500 | 46500 |  |  | N/A | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-09 | Completed
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTRATION (JAPANESE CAKE MAKING) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  | 2023-05-23 | 2023-05-24 | 2023-05-24 |  |  | 2023-08-24 | 2023-08-24 | Government of the Philippines (current year's budget) | 6940 | 6940 |  | 6720 | 6720 |  |  | N/A | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-24 | Completed
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTRATION (PICHI-PICHI MAKING) | JENEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  | 2023-08-23 | 2023-08-23 | Government of the Philippines (current year's budget) | 7310 | 7310 |  | 6940 | 6940 |  |  | N/A | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | Completed
310300100001000 | CONSUMABLES FOR PROVINCIAL SKILLS DEMONSTRATION 2023 COOKERY | GRETCHEN J. NUBOG | No | NP-53.9 - Small Value Procurement | 2023-08-24 | 2023-08-24 |  | 2023-08-24 | 2023-08-24 | 2023-08-24 |  | 2023-08-24 | 2023-08-24 | 2023-08-24 |  |  |  | 2023-08-23 | 2023-08-14 | 2023-08-24 |  |  | 2023-08-24 | 2023-08-24 | Government of the Philippines (current year's budget) | 10809 | 10809 |  | 10734.5 | 10734.5 |  |  | N/A | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-24 | Completed
310300100001000 | FOR GRASS CUTTER USE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-08-25 | N/A |  |  | 2023-08-25 | 2023-08-25 | Government of the Philippines (current year's budget) | 1626.8 | 1626.8 |  | 126.8 | 126.8 |  |  | N/A | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-25 | Completed
310300100001000 | CONSUMABLES, TOOLS, AND EQUIPMENT FOR THE PROVINCIAL SKILLS COMOPETITION 2023 FOR PATTESERIE CONFECTIONARY ENERGY | CARMIFLOR M. ANDAYA | No | NP-53.9 - Small Value Procurement | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  | 2023-08-24 | 2023-08-24 | Government of the Philippines (current year's budget) | 49011 | 49011 |  | 48562 | 48562 |  |  | N/A | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-24 | Completed
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTRATION TAILORING | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  | 2023-08-22 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-25 | 2023-08-25 | Government of the Philippines (current year's budget) | 2234 | 2234 |  | 2234 | 2234 |  |  | N/A | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-25 | Completed
310300100001000 | CONSUMABLES FOR VEHICLE SERVICES | EDUARDO A. PEPINO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-08-31 | N/A |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 27983.04 | 27983.04 |  | 27983.04 | 27983.04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | Completed
310300100001000 | MINERAL WATER SUPPLY | LYNDRE G. BAYOTAS | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-09-01 | N/A |  |  | 2023-02-09 | 2023-02-09 | Government of the Philippines (current year's budget) | 12581.85 | 12581.85 |  | 12581.85 | 12581.85 |  |  | N/A | N/A | N/A | N/A | N/A | M | 2023-09-02 | Completed
310300100001000 | ASSESSMENT MEALS AND SNACKS | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-09-04 | 2023-09-04 |  | 2023-09-04 | 2023-09-04 | 2023-09-04 |  | 2023-09-04 | 2023-09-04 | 2023-09-04 |  |  |  | 2023-09-05 | 2023-09-08 | 2023-09-08 |  |  | 2023-09-10 | 2023-09-10 | Government of the Philippines (current year's budget) | 5100 | 5100 |  | 5100 | 5100 |  |  | N/A | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-10 | Completed
310300100001000 | CONSUMABLES, TOOLS AND EQUIPMENT FOR HOUSEKEEPING WATER SUPPLY | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  | 2023-08-14 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-26 | 2023-08-26 | Government of the Philippines (current year's budget) | 391100 | 391100 |  | 376465 | 376465 |  |  | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-26 | Completed
310300100001000 | CONSUMABLES FOR CARPENTRY NC II- ASSESSMENT USE (CACW- COMPETENCY ASSESSMENT AND CERTIFICATION FOR WORKER | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  | 2023-08-10 | 2023-08-14 | 2023-08-14 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 9175 | 9175 |  | 6855 | 6855 |  |  | N/A | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-31 | Completed
310300100001000 | CONSUMABLES FOR THE PROVINCIAL SKILLS COMPETITION 2023 RESTAURENT SERVICES | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  | 2023-05-23 | 2023-08-24 | 2023-05-24 |  |  | 2023-08-25 | 2023-08-25 | Government of the Philippines (current year's budget) | 33710 | 33710 |  | 33699 | 33699 |  |  | N/A | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-05-25 | Completed
310300100001000 | CONSUMABLES FOR CARPENTRY NC II- ASSESSMENT USE (SCHOLAR'S STEP /RL-20) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  | 2023-08-10 | 2023-08-14 | 2023-08-14 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 18350 | 18350 |  | 13710 | 13710 |  |  | N/A | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-31 | Completed
310300100001000 | LED WALL RENTAL, POLO SHIRT SUBLIMATION AND DECORATION MATERIALS FOR ZAMPEN FRIENDSHIP GAMES | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  | 2023-08-14 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 24000 | 24000 |  | 23650 | 23650 |  |  | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-16 | Completed
310300100001000 | MATERIALS FOR ZSPI ELECTRICAL MAINTENANCE | RONNEL B. PEPINO | No | NP-53.9 - Small Value Procurement | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  | 2023-08-11 | 2023-08-16 | 2023-08-16 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 47990 | 47990 |  | 43955 | 43955 |  |  | N/A | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-16 | Completed
310300100001000 | OFFICE SUPPLIES AND EQUIPMENT FOR ASSESSMENT CENTER (3RD QUARTER) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  | 2023-08-22 | 2023-08-25 | 2023-08-25 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 49250 | 49250 |  | 49250 | 49250 |  |  | N/A | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-10-12 | Completed
310300100001000 | CONSUMABLES FOR SKILLS TRAINING AT IMELDA, ZAMBOANGA SIBUGAY | JENEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  |  |  | 2023-09-08 | 2023-08-09 | 2023-08-09 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 3046.25 | 3046.25 |  | 2998 | 2998 |  |  | N/A | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-11 | Completed
310300100001000 | CONSUMABLES FOR THE PROVINCIAL SKILLS COMPETITION 2023 FOR BAKERY | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  | 2023-08-23 | 2023-08-23 | Government of the Philippines (current year's budget) | 12590 | 12590 |  | 10165.4 | 10165.4 |  |  | N/A | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | Completed
310300100001000 | OFFICE EQUIPMENT FOR AOIV/HR OFFICE | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | 2023-09-01 | 2023-09-01 |  |  |  | 2023-09-01 | 2023-09-04 | 2023-09-04 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 49400 | 49400 |  | 46350 | 46350 |  |  | N/A | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-26 | Completed
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTRATION FOUNDATION DAY (ICED COFFEE) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 12185 | 12185 |  | 8381 | 8381 |  |  | N/A | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-18 | Completed
310300100001000 | MEALS AND SNACKS FOR ZSPI - YEAR END PERFORMANCE ASSESSMENT | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-12-19 | 2023-12-19 |  | 2023-12-19 | 2023-12-19 | 2023-12-19 |  | 2023-12-19 | 2023-12-19 | 2023-12-19 |  |  |  | 2023-12-19 | 2023-12-20 | 2023-12-20 |  |  | 2023-12-21 | 2023-12-21 | Government of the Philippines (current year's budget) | 49940 | 49940 |  | 49500 | 49500 |  |  | N/A | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-21 | Completed
310300100001000 | CONSUMABLES FOR REGIONAL SKILLS COMPETITION 2023 (CNC) | BRYLE F. BARRIOS | No | NP-53.9 - Small Value Procurement | 2023-09-21 | 2023-09-21 |  | 2023-09-21 | 2023-09-21 | 2023-09-21 |  | 2023-09-21 | 2023-09-21 | 2023-09-21 |  |  |  | 2023-09-22 | 2023-09-25 | 2023-09-25 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 9900 | 9900 |  | 9885 | 9885 |  |  | N/A | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-26 | Completed
310300100001000 | CONSUAMBLES FOR COMMUNITY BASED TRAINING FOR PANTAWID BENIFICIACIES (BANANA CHIPS MAKING) | MAE JANE G. DAGUPAN | No | NP-53.9 - Small Value Procurement | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  |  |  | 2023-11-17 | 2023-11-20 | 2023-11-20 |  |  | 2023-12-15 | 2023-12-15 | Government of the Philippines (current year's budget) | 9350 | 9350 |  | 7762 | 7762 |  |  | N/A | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-12-15 | Completed
310300100001000 | MATERIALS FOR EIM - 3RD QUARTER | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-11-14 | 2023-11-14 |  | 2023-11-14 | 2023-11-14 | 2023-11-14 |  | 2023-11-14 | 2023-11-14 | 2023-11-14 |  |  |  | 2023-11-14 | 2023-11-14 | 2023-11-14 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 282000 | 282000 |  | 204400 | 204400 |  |  | N/A | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-12-11 | Completed
310300100001000 | SUPPLIES , TOOLS, AND EQUIPMENT FOR SCHOOL REPAIR MAINTENANCE - 3RD QUARTER | ROBERTO B. LUNA | No | NP-53.9 - Small Value Procurement | 2023-11-22 | 2023-11-22 |  | 2023-11-22 | 2023-11-22 | 2023-11-22 |  | 2023-11-22 | 2023-11-22 | 2023-11-22 |  |  |  | 2023-11-22 | 2023-11-27 | 2023-11-27 |  |  | 2023-12-28 | 2023-12-28 | Government of the Philippines (current year's budget) | 203500 | 203500 |  | 162740 | 162740 |  |  | N/A | 2023-11-22 | 2023-11-22 | 2023-11-22 | 2023-11-22 | 2023-11-22 | 2023-12-28 | Completed
310300100001000 | SUPPLIES FOR DRIVING NC II TRAINING | RICKY O. DAG-UMAN | No | NP-53.9 - Small Value Procurement | 2023-11-24 | 2023-11-24 |  | 2023-11-24 | 2023-11-24 | 2023-11-24 |  | 2023-11-24 | 2023-11-24 | 2023-11-24 |  |  |  | 2023-11-24 | 2023-11-27 | 2023-11-27 |  |  | 2023-12-01 | 2023-12-01 | Government of the Philippines (current year's budget) | 39850 | 39850 |  | 38685 | 38685 |  |  | N/A | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-12-01 | Completed
310300100001000 | SUPPLIES, MATERIALS, TOOLS AND EQUIPMENT FOR CSS NCII UPGRADE OF TRAINING FACILITY 2023 | JOSEPH D. VELASCO | No | NP-53.9 - Small Value Procurement | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-19 | 2023-09-19 |  |  |  | 2023-09-21 | 2023-09-25 | 2023-09-25 |  |  | 2023-12-17 | 2023-12-17 | Government of the Philippines (current year's budget) | 60000 | 60000 |  | 51000 | 51000 |  |  | N/A | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-12-14 | Completed
310300100001000 | VENUE RENTAL FOR ZSPI YEAR END PERFORMANCE ASSESSMENT | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-12-18 | 2023-12-18 |  | 2023-12-18 | 2023-12-18 | 2023-12-18 |  | 2023-12-18 | 2023-12-18 | 2023-12-18 |  |  |  | 2023-12-18 | 2023-12-19 | 2023-12-19 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 32500 | 32500 |  | 31500 | 31500 |  |  | N/A | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2023-12-19 | Completed
310300100001000 | OFFICE SUPPLIES AND EQUIPMENT FOR CASHIERS | AILEEN A. CORDOVA | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  |  | 2023-11-07 | 2023-11-10 | 2023-11-10 |  |  | 2024-02-14 | 2024-02-14 | Government of the Philippines (current year's budget) | 51150 | 51150 |  | 40745 | 40745 |  |  | N/A | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2024-02-14 | Completed
310300100001000 | CONSUMABLES FOR FBS NC II COMBASED NC II IN 20 BARANGAYS | DON ADAM B. DETABLAN | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-11-29 | 2023-11-29 |  |  |  | 2023-11-29 | 2023-11-30 | 2023-11-29 |  |  | 2024-01-31 | 2024-01-31 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 5620 | 5620 |  |  | N/A | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2024-01-31 | Completed
310300100001000 | GIFT CERTIFICATE FOR 2023 TESDA LOYALTY AWARDEE | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-12-13 | 2023-12-13 |  | 2023-12-13 | 2023-12-13 | 2023-12-13 |  | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-13 | 2023-12-14 | 2023-12-14 |  |  | 2024-02-07 | 2024-02-07 | Government of the Philippines (current year's budget) | 25000 | 25000 |  | 24500 | 24500 |  |  | N/A | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2024-02-07 | Completed
310300100001000 | NATIONAL COMPETENCY ASSSESSMENT CONSUMABLES FOR BPP NCII (PESF (ITTC-20, TIZAP21, WESTMIN 25) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  |  | 2023-07-12 | 2023-07-15 | 2023-07-15 |  |  | 2023-08-04 | 2023-08-04 | Government of the Philippines (current year's budget) | 14130 | 14130 |  | 11909.04 | 11909.04 |  |  | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-08-04 | Completed
310300100001000 | CONSUMABLES FOR COMMUNITY BASED TRAINING AT TIPAN,NAGA ZSP | JENNEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2024-03-07 | 2024-03-07 |  | 2024-03-07 | 2024-03-07 | 2024-03-07 |  | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 | 2024-03-11 | 2024-03-11 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philippines (current year's budget) | 560 | 560 |  | 469 | 469 |  |  | N/A | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-11 | Completed
310300100001000 | CONSUMABLES FOR THE CONDUCT OF COMMUNITY BASED TRAINING FOR LEMON JUICE MAKING ON MARCH 12,2024 AT TIPAN, NAGA, ZSP | GRETCHEN J. NUBOG | No | NP-53.9 - Small Value Procurement | 2024-03-07 | 2024-03-07 |  | 2024-03-07 | 2024-03-07 | 2024-03-07 |  | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 | 2024-03-11 | 2024-03-11 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philippines (current year's budget) | 4820 | 4820 |  | 4813 | 4813 |  |  | N/A | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-11 | Completed
310300100001000 | CONSUMABLES FOR VEHICLE SERVICES | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N | N/A |  |  | 2024-02-26 | 2024-02-26 | Government of the Philippines (current year's budget) | 22672.14 | 22672.14 |  | 22672.14 | 22672.14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | Completed
310300100001000 | CONSUMABLES FOR CARPENTRY NC II- ASSESSMENT USE DIPLOMA (SECTION B-23 DCET 1ST YR | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 | 2024-02-12 | 2024-02-12 |  |  | 2024-02-16 | 2024-02-16 | Government of the Philippines (current year's budget) | 10325 | 10325 |  | 7175 | 7175 |  |  | N/A | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-16 | Completed
310300100001000 | NATIONAL COMTENCY ASSESSMENT CONSUMABLES FOR EIM NC II (DIPLOMA SECTION B- 25 DCET 1 YR) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 | 2024-02-12 | 2024-02-12 |  |  | 2024-02-23 | 2024-02-23 | Government of the Philippines (current year's budget) | 26950 | 26950 |  | 25075 | 25075 |  |  | N/A | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-23 | Completed
310300100001000 | CONSUMEBLES FOR ASSESSMENT IN MASONRY NC II | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2024-02-23 | N/A |  |  | 2024-02-23 | 2024-02-23 | Government of the Philippines (current year's budget) | 976.08 | 976.08 |  | 976.08 | 976.08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | Completed
310300100001000 | CONSUMABLES FOR COMMUNITY BASED TRAINING @ IPIL HEIGHTS, IPIL ZSP (BREAD AND CAKE MAKING | CARMIFLOR M. ANDAYA | No | NP-53.9 - Small Value Procurement | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  |  |  | 2023-09-26 | 2023-09-27 | 2023-03-27 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 14888 | 14888 |  | 14691 | 14691 |  |  | N/A | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-28 | Completed
310300100001000 | CONSUMABLES FOR SERVICES VEHICLE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2024-02-12 | N/A |  |  | 2024-02-13 | 2024-02-13 | Government of the Philippines (current year's budget) | 10739.84 | 10739.84 |  | 10739.84 | 10739.84 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | Completed
310300100001000 | CONSUMABLES FOR ZSPI GROUND MAINTENANCE (GRASS CUTTER USE) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2024-02-26 | N/A |  |  | N/A | 2024-02-27 | Government of the Philippines (current year's budget) | 2440 | 2440 |  | 2440 | 2440 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | Completed
310300100001000 | ACRYLIC SIGNAGES FOR ADMIN OFFICE | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2024-02-19 | 2024-02-19 |  | 2024-02-19 | 2024-02-19 | 2024-02-19 |  | 2024-02-19 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-20 | 2024-02-23 | 2024-02-23 |  |  | 2024-03-12 | 2024-03-12 | Government of the Philippines (current year's budget) | 39500 | 39500 |  | 26000 | 26000 |  |  | N/A | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-03-12 | Completed
310300100001000 | TARPAULIN FOR PREPARATION OF RD TAHARTA S. MAPANDI VISIT | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-01-31 |  | 2024-01-31 | 2024-01-31 | 2024-01-31 |  | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-01-31 | 2024-02-01 | 2024-01-02 |  |  | 2024-01-02 | 2024-01-02 | Government of the Philippines (current year's budget) | 3960 | 3960 |  | 3390 | 3390 |  |  | N/A | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-01 | Completed
310300100001000 | PHOTOCOPIER SPACE PARTS REPLACEMENT AT ASSESSMENT CENTER OFFICE | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-10-20 | 2023-10-20 |  | 2023-10-20 | 2023-10-20 | 2023-10-20 |  | 2023-10-20 | 2023-10-20 | 2023-10-20 |  |  |  | N/A | 10/23/23 | N/A |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 5699.68 | 5699.68 |  | 5699.68 | 5699.68 |  |  | N/A | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2023-11-17 | Completed
310300100001000 | ASSESSMENT CONSUMABLES FRO MASONRY NC II -20 TWSP | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 | 2024-02-12 | 2024-02-12 |  |  | 2024-02-15 | 2024-02-15 | Government of the Philippines (current year's budget) | 17650 | 17650 |  | 12400 | 12400 |  |  | N/A | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-15 | Completed
310300100001000 | SUPPLIES TOOLS AND EQUIPMENT FOR EPAS NC II | PEPITO B. PAGAYON | No | NP-53.9 - Small Value Procurement | 2023-11-20 | 2023-11-20 |  | 2023-11-20 | 2023-11-20 | 2023-11-20 |  | 2023-11-20 | 2023-11-20 | 2023-11-20 |  |  |  | 2023-11-21 | 2023-11-24 | 2023-11-24 |  |  | 2024-02-26 | 2024-02-26 | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 291310 | 291310 |  |  | N/A | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2024-02-26 | Completed
310300100001000 | CONSUMABLES TOOLS AND EQUIPMENT FOR REGIONAL SKILLS COMPETTITION 2023(RESTAURANT SERVICES) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  |  | 2023-09-14 | 2023-09-18 | 2023-09-18 |  |  | 2023-10-16 | 2023-10-16 | Government of the Philippines (current year's budget) | 138335 | 138335 |  | 134400 | 134400 |  |  | N/A | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-10-16 | Completed
310300100001000 | MEALS AND SNACKS FOR TRAINERS TRAINING IN CONSTRUCTION PAINTING | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  | 2023-12-17 | 2023-12-17 | Government of the Philippines (current year's budget) | 27000 | 27000 |  | 27000 | 27000 |  |  | N/A | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-07 | Completed
310300100001000 | CONSUMABLES FOR AUTOMOTIVE TRAINING AREA REPAIR AND MAINTENANCE | OSWALDO M. DECHETA | No | NP-53.9 - Small Value Procurement | 2023-09-28 | 2023-09-28 |  | 2023-09-28 | 2023-09-28 | 2023-09-28 |  | 2023-09-28 | 2023-09-28 | 2023-09-28 |  |  |  | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-27 | 2023-10-27 | Government of the Philippines (current year's budget) | 33800 | 33800 |  | 28640 | 28640 |  |  | N/A | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-10-27 | Completed
310300100001000 | FOR SCHOOL VEHICLE SERVICE WITH PLATE NO. GAN 2367 | EDEN A. MONGCOPA | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | NB | N/A | N/A |  |  |  | N/A | 2023-12-29 | 2023-12-29 |  |  | 2023-12-29 | 2912/23 | Government of the Philippines (current year's budget) | 29297.04 | 29297.04 |  | 29297.04 | 29297.04 |  |  | N/A | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-12-29 | Completed
310300100001000 | CONSUMABLES FOR ONE DAY T6RAINING COMBASED PROGRAM AT ALIVE BAPTIST CHURCH WOMEN (BANANA CHIPS MAKING) | UZZIEL C. GUERRERU | No | NP-53.9 - Small Value Procurement | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | 2023-12-01 | 2023-12-01 |  |  |  | 2023-12-01 | 2023-12-02 | 2023-12-02 |  |  | 2023-12-03 | 2023-12-03 | Government of the Philippines (current year's budget) | 1040 | 1040 |  | 1016 | 1016 |  |  | N/A | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-03 | Completed
310300100001000 | CONSUMABLES FOR COMNMUNITY BASED TRAINING (DSWD) | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  |  |  | 2023-11-17 | 2023-11-20 | 2023-11-20 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 18660 | 18660 |  | 14539.9 | 14539.9 |  |  | N/A | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-20 | Completed
310300100001000 | MEALS AND SNACKS FOR TRAINERS IN TMC LEVEL II | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  | 2024-12-07 | 2024-12-07 | Government of the Philippines (current year's budget) | 31500 | 31500 |  | 31500 | 31500 |  |  | N/A | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2024-12-17 | Completed
310300100001000 | OFFICE EQUIPMENT AND DEVICE FOR BPP NC II INSTRUCTIONAL PURPOSES | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10 | 2023-11-10 |  |  |  | 2023-11-13 | 2023-11-16 | 2023-11-16 |  |  | 2023-01-19 | 2023-01-19 | Government of the Philippines (current year's budget) | 55500 | 55500 |  | 46000 | 46000 |  |  | N/A | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-01-19 | Completed
310300100001000 | CONSUMABLES, TOOLS, & EQUIPMENT NC II AND ROOM MAINTENANCE | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-09-26 | 2023-09-26 |  |  |  | 2023-09-26 | 2023-09-29 | 2023-09-29 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 126877 | 126877 |  | 124020 | 124020 |  |  | N/A | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-11-20 | Completed
310300100001000 | CONSUMABLES FOR TESDA REGIONAL SERVICE VEHICLE PLATE NUMBER SAB4230 | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-09-13 | 2023-09-13 |  | 2023-09-13 | 2023-09-13 | 2023-09-13 |  | 2023-09-13 | 2023-09-13 | 2023-09-13 |  |  |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  | 2023-12-10 | 2023-12-10 | Government of the Philippines (current year's budget) | 9477.6 | 9477.6 |  | 9477.6 | 9477.6 |  |  | N/A | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-12-10 | Completed
310300100001000 | MEALS AND SNACKS FOR THE CONDUCT OF OCULAR INSPECTIONIN DIFFERENT QUALIFICATION (PLUMBING NC I, PLUMBNING NC II, PLUAMBING NC III) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-12-09 | 2023-12-09 |  | 2023-12-09 | 2023-12-09 | 2023-12-09 |  | 2023-12-09 | 2023-12-09 | 2023-12-09 |  |  |  | 2023-12-09 | 2023-11-30 | 2023-11-30 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 3250 | 3250 |  | 3250 | 3250 |  |  | N/A | 2023-12-09 | 2023-12-09 | 2023-12-09 | 2023-12-09 | 2023-12-09 | 2023-12-14 | Completed
310300100001000 | OFFICE SUPPLIES AND MAINTENANCE FOR BILLING OFFICE | AILEEN A. CORDOVA | No | NP-53.9 - Small Value Procurement | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  |  | 2023-07-11 | 2023-11-10 | 2023-11-10 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 51450 | 51450 |  | 50693 | 50693 |  |  | N/A | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-12-13 | Completed
310300100001000 | CONSUMABLES FOR ZSPI GROUND MAINTENANCE (GRASS CUTTER USE) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N | N/A | N/A |  |  |  | N/A | 2023-12-22 | N/A |  |  | 2023-12-01 | 2023-12-01 | Government of the Philippines (current year's budget) | 406.7 | 406.7 |  | 406.7 | 406.7 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | Completed
310300100001000 | MINERAL WATER SUPPLY | LYNDRE G. BAYOTAS | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-12-29 | 2023-12-29 |  |  | 2023-12-28 | 2023-12-28 | Government of the Philippines (current year's budget) | 3644 | 3644.2 |  | 3644.2 | 3644.2 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | Completed
310300100001000 | TARPAULIN, OFFICE SUPPLIES, MEALS, AND SNACKS FOR ZSPI SCHOOL PUBLICATION TRANING AND WORKSHOP | JOHN MICHAEL L. MOMTILLANO | No | NP-53.9 - Small Value Procurement | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10 | 2023-11-10 |  |  |  | 2023-11-06 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-10 | 2023-11-10 | Government of the Philippines (current year's budget) | 41920 | 41920 |  | 40800 | 40800 |  |  | N/A | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-11-10 | Completed
310300100001000 | MEALS AND SNACKS FOR TILE SETTING TRAINING NO. 25-26,2023 | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-11-23 | 2023-11-23 |  | 2023-11-23 | 2023-11-23 | 2023-11-23 |  | 2023-11-23 | 2023-11-23 | 2023-11-23 |  |  |  | 2023-11-23 | 2023-11-24 | 2023-11-24 |  |  | 2023-11-25 | 2023-11-25 | Government of the Philippines (current year's budget) | 27000 | 27000 |  | 27000 | 27000 |  |  | N/A | 2023-11-23 | 2023-11-23 | 2023-11-10 | 2023-11-23 | 2023-11-23 | 2023-11-26 | Completed
310300100001000 | MINERAL WATER SUPPLY | LYNDRE G. BAYOTAS | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-01 | 2023-12-01 | Government of the Philippines (current year's budget) | 14389.78 | 14389.78 |  | 14389.78 | 14389.78 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | Completed
310300100001000 | SUPPLIES AND MATERIALS FOR TILE FLOORING IN EPAS NC II LABORATORY/WORKSHOP | ORLANDO B. TOMAS | No | NP-53.9 - Small Value Procurement | 2023-11-24 | 2023-11-24 |  | 2023-11-24 | 2023-11-24 | 2023-11-24 |  | 2023-11-24 | 2023-11-24 | 2023-11-24 |  |  |  | 2023-11-24 | 2023-11-28 | 2023-11-28 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 500100 | 500100 |  | 463100 | 463100 |  |  | N/A | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-12-06 | Completed
310300100001000 | CONSUMABLES, TOOLS, AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (RESTAURANT) | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-09-13 | 2023-09-13 |  | 2023-09-13 | 2023-09-13 | 2023-09-13 |  | 2023-09-13 | 2023-09-13 | 2023-09-13 |  |  |  | 2023-09-14 | 2023-09-18 | 2023-09-18 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 126140 | 126140 |  | 89613 | 89613 |  |  | N/A | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-10-20 | Completed
310300100001000 | MATERIALS, TOOLS AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (ELECTRONICS) | ORLANDO B. TOMAS | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-09 | 2023-10-09 |  | 2023-10-09 | 2023-10-09 | 2023-10-10 |  |  |  | 2023-10-13 | 2023-10-13 | 2023-10-13 |  |  | 2023-12-21 | 2023-12-21 | Government of the Philippines (current year's budget) | 236350 | 236350 |  | 223700 | 223700 |  |  | N/A | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-12-21 | Completed
310300100001000 | CONSUMANBLES FOR REGIONAL SKILLS COMPETITION (LELECTRICAL MAINTENANCE) | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | 2023-10-11 | 2023-10-11 |  | 2023-10-11 | 2023-10-11 | 2023-10-11 |  | 2023-10-11 | 2023-10-11 | 2023-10-11 |  |  |  | 2023-10-12 | 2023-10-16 | 2023-10-16 |  |  | 2023-10-26 | 2023-10-26 | Government of the Philippines (current year's budget) | 152260 | 152260 |  | 80945 | 80945 |  |  | N/A | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-26 | Completed
310300100001000 | CONSUMABLES FOR 200 BARANGAYS IN PILLOW CASE MAKING | MALARE P. COTEJO | No | NP-53.9 - Small Value Procurement | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  | 2023-11-17 | 2023-11-17 | 2023-11-17 |  |  |  | 2023-11-17 | 2023-11-20 | 2023-11-20 |  |  | 2023-11-22 | 2023-11-22 | Government of the Philippines (current year's budget) | 31600 | 31600 |  | 28805 | 28805 |  |  | N/A | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-22 | Completed
310300100001000 | CONSUMABLES FOR CSS NC II TRAINING (BATCH 4) 2023 | JOSEPH D. VELASCO | No | NP-53.9 - Small Value Procurement | 2023-09-18 | 2023-09-18 |  | 2023-09-18 | 2023-09-18 | 2023-09-18 |  | 2023-09-18 | 2023-09-18 | 2023-09-18 |  |  |  | 2023-09-18 | 2023-09-22 | 2023-09-22 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 66200 | 66200 |  | 60180 | 60180 |  |  | N/A | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-11-29 | Completed
310300100001000 | MATERIALS,TOOLS AND EQUIPMENT FOR EIM NC II (TRAINING CUM PRODUCTION) | RHANDO O. SANGCOM | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-21 | 2023-11-21 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 |  | 2023-11-21 | 2023-11-21 | 2023-11-21 |  |  |  | 2023-11-21 | 2023-11-24 | 2023-11-24 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 51800 | 51800 |  | 43500 | 43500 |  |  | N/A | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-12-13 | Completed
310300100001000 | SUPPLIES TOOLS AND EQUIPMENT FOR EPAS NC II | PEPITO B. PAGAYON | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-20 | 2023-11-20 |  | 2023-11-20 | 2023-11-20 | 2023-11-20 |  | 2023-11-20 | 2023-11-20 | 2023-11-20 |  |  |  | 2023-11-21 | 2023-11-24 | 2023-11-24 |  |  | 2023-01-15 | 2023-01-15 | Government of the Philippines (current year's budget) | 97000 | 97000 |  | 77500 | 77500 |  |  | N/A | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-01-15 | Completed
310300100001000 | UTPRAS REGISTRATION PRE-INSPECTION (MEALS AND SNACKS) | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-11-13 | 2023-11-13 |  | 2023-11-13 | 2023-11-13 | 2023-11-13 |  | 2023-11-13 | 2023-11-13 | 2023-11-13 |  |  |  | 2023-11-23 | 2023-11-13 | 2023-11-13 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 7500 | 7500 |  | 7500 | 7500 |  |  | N/A | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-15 | Completed
310300100001000 | TARPAULIN FOR ZSPI SITE DEVELOPMENT PLAN MAP, BASO AND OTHER SIGNAGES | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  | 2023-08-11 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 11870 | 11870 |  | 11611 | 11611 |  |  | N/A | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-15 | Completed
310300100001000 | SUPPIES FOR MAKING BASE FOR WATER TANK STORAGR WITH COMPLETE FITTING PIPE CONNECTION | ROBERTO B. LUNA | No | NP-53.9 - Small Value Procurement | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  |  |  | 2023-10-13 | 2023-10-18 | 2023-10-18 |  |  | 2023-12-01 | 2023-12-01 | Government of the Philippines (current year's budget) | 152450 | 152450 |  | 141455 | 141455 |  |  | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-01-12 | Completed
310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NC II- STEP SCHOLARSHIP (STII-100 CANDIDATES) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  | 2023-10-12 | 2023-10-12 | 2023-10-12 |  |  |  | 2023-08-02 | 2023-08-05 | 2023-08-05 |  |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 20875 | 20875 |  | 16794 | 16794 |  |  | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-08-30 | Completed
310300100001000 | CONSUMABLES COST OF TRANSLUCENT MINI LATHE MACHINE SIMULATOR | BRYLE F. BARRIOS | No | NP-53.9 - Small Value Procurement | 2023-05-20 | 2023-05-20 |  | 2023-05-20 | 2023-05-20 | 2023-05-20 |  | 2023-05-20 | 2023-05-20 | 2023-05-20 |  |  |  | 2023-05-25 | 2023-05-30 | 2023-05-30 |  |  | 31/5/23. | 2023-05-31 | Government of the Philippines (current year's budget) | 32000 | 32000 |  | 32000 | 32000 |  |  | N/A | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-31 | Completed
310300100001000 | CONSUMABLES FOR SKILLS DEMONSTARTION FOUNDATION DAY (ICED COFFE) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  | 2023-09-08 | 2023-09-08 | Government of the Philippines (current year's budget) | 12185 | 12185 |  | 8381.74 | 8381.74 |  |  | N/A | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-18 | Completed
310300100001000 | OFFICE EQUIPMENT FOR AO/HR OFFICE | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | 2023-09-01 | 2023-09-01 |  |  |  | 2023-09-01 | 2023-09-04 | 2023-09-04 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 49400 | 49400 |  | 46350 | 46350 |  |  | N/A | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-26 | Completed
310300100001000 | CONSUMABLES FOR THE PROVINCIAL SKILLS COMPETITION 2023 FOR BAKERY | AILEENE A. DACULA | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  | 2023-08-23 | 2023-08-23 | Government of the Philippines (current year's budget) | 11590 | 11590 |  | 10165.4 | 10165.4 |  |  | N/A | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-23 | Completed
310300100001000 | COMNSUMABLES FOR SKILLS TRAINING AT IMELDA, ZAMBOANGA SIBUGAY | JENEBELLE T. CONAHAP | No | NP-53.9 - Small Value Procurement | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  |  |  | 2023-09-08 | 2023-09-08 | 2023-09-08 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 3046.25 | 3046.25 |  | 2998 | 2998 |  |  | N/A | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-11 | Completed
310300100001000 | OFFICE SUPPLIES AND EQUIPMENT FOR ASSESSMENT CENTER 3RD QUARTER | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  | 2023-08-22 | 2023-08-25 | 2023-08-25 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 49250 | 49250 |  | 49250 | 49250 |  |  | N/A | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-10-12 | Completed
310300100001000 | LED WALL RENTAL, POLO SHIRT SUBLIMATION AND DECORATION MATERIALS FOR ZAMPEN FRIENDSHIP GAMES | PRESCO P. CANETE | No | NP-53.9 - Small Value Procurement | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  | 2023-08-14 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 24000 | 24000 |  | 23650 | 23650 |  |  | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-16 | Completed
310300100001000 | CONSUMABLES FOR CARPENTRY NC II ASSESSMENT USE (SCHOOLAR'S STEP /RL-20) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  | 2023-08-10 | 2023-08-14 | 2023-08-14 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 18350 | 18350 |  | 13710 | 13710 |  |  | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-31 | Completed
310300100001000 | CONSUMABLES FOR THE PROVINCIAL SKILLS COMPETITION 2023 RESTAURENT SERVICES | MAY P. COMEDIDO | No | NP-53.9 - Small Value Procurement | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  | 2023-05-23 | 2023-08-24 | 2023-08-24 |  |  | 2023-08-25 | 2023-08-25 | Government of the Philippines (current year's budget) | 33710 | 33710 |  | 33699 | 33699 |  |  | N/A | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-23 | 2023-08-25 | Completed
310300100001000 | CONSUMABLES, TOOLS AND EQUIPMENT AND TRAINING FOR HOUSEKEEPING WATER SUPPLY | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  | 2023-08-14 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-26 | 2023-08-26 | Government of the Philippines (current year's budget) | 391100 | 391100 |  | 376465 | 376465 |  |  | N/A | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-26 | Completed
310300100001000 | CONSUAMBLES FOR CARPENTRY NC II - ASSESSMENT USE (CAWCW- COMPETENCY ASSESSMENT AND CERTIFICATION FOR WORKER) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  | 2023-08-10 | 2023-08-14 | 2023-08-14 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 9175 | 9175 |  | 6855 | 6855 |  |  | N/A | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-31 | Completed
310300100001000 | ASSESSMENT MEALS AND SNACKS | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-09-04 | 2023-09-04 |  | 2023-09-04 | 2023-09-04 | 2023-09-04 |  | 2023-09-04 | 2023-09-04 | 2023-09-04 |  |  |  | 2023-09-05 | 2023-09-08 | 2023-09-08 |  |  | 2023-09-10 | 2023-09-10 | Government of the Philippines (current year's budget) | 5100 | 5100 |  | 5100 | 5100 |  |  | N/A | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-04 | 2023-09-10 | Completed
310300100001000 | MINERAL WATER SUPPLY | LYNDRE G. BAYOTAS | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | 2023-09-01 | 2023-09-01 |  |  | 2023-09-02 | 2023-09-02 | Government of the Philippines (current year's budget) | 12581.85 | 12581.85 |  | 12581.85 | 12581.85 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 02/9/523 | Completed
310300100001000 | CONSUMABLES FOR VEHICLE SERVICES | EDUARDO A. PEPINO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N | N/A | N/A |  |  |  | N/A | 2023-08-31 | N/A |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 27983.04 | 27983.04 |  | 27983.04 | 27983.04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | Completed
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000
310300100001000 | FOR SCHOOL VEHICLE SERVICE WITH PLATE NO. GAN 2367 | EDUARDO A. PEPINO | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | 2023-08-13 | 2023-08-13 | N/A |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 18527.1 | 18527.1 |  | 18527.1 | 18527.1 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | Completed | FALSE | FALSE
[25 empty] | Total Allotted Budget of Procurement Activities | 21618191.17 | 21618191.37 | 0 |  |  |  | 12.45%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 18926420.72 | 18926420.72 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 2691770.45 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
| ELECTRICAL REPAIR AND MAINTENANCE OF ZSPI |  | No | NP-53.9 - Small Value Procurement | 2023-04-23 | 2023-04-23 |  | 2023-04-23 | 2023-04-23 | 2023-04-23 |  | 2023-04-23 | 2023-04-23 | 2023-04-23 |  |  |  | 2024-04-24 | 2024-04-29 | 2024-04-29 |  |  | N/A | N/A | TF | 844140 | 844140 |  | 820700 | 820700 |  |  | N/A | 2023-04-23 | 2023-04-23 | 2023-04-23 | 2023-04-23 | 2023-04-23 | N/A
| DINNER FOR CENTRAL OFFICE PERSONNEL VISIT |  | No | NP-53.9 - Small Value Procurement | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 |  |  |  | 2024-05-14 | 2024-05-14 | 2024-05-14 |  |  | 2024-05-16 | 2024-05-16 | TF | 6560 | 6560 |  | 6560 | 6560 |  |  | N/A | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-16
| MEALS AND SNACKS FOR STAR/SEAL OF INTERGRITY ORIENTATION |  | No | NP-53.9 - Small Value Procurement | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 |  |  |  | 2024-05-23 | 2024-05-24 | 2024-05-24 |  |  | 2024-05-25 | 2024-05-25 | TF | 22500 | 22500 |  | 22500 | 22500 |  |  | N/A | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-25
| SNACKS FOR 3D PRINTING WORKSHOP/SEMINAR |  | No | NP-53.9 - Small Value Procurement | 2024-05-20 | 2024-05-20 |  | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-05-20 | 2024-05-20 | 2024-05-20 |  |  |  | 2024-05-20 | 2024-05-21 | 2024-05-24 |  |  | 2024-05-22 | 2024-05-22 | TF | 6000 | 6000 |  | 6000 | 6000 |  |  | N/A | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-22 | 2024-05-22
| MEALS AND SNACKS FOR CHED EVALUATION AND INVENTORY |  | No | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-02 | 2024-04-05 | 2024-04-05 |  |  | 2024-04-06 | 2024-04-06 | TF | 20250 | 20250 |  | 20250 | 20250 |  |  | N/A | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06
| NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NC II- 50 CANDIDATES |  | No | NP-53.9 - Small Value Procurement | 2024-05-24 | 2024-05-24 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 |  |  |  | 2024-05-27 | 2024-05-27 | 2024-05-27 |  |  | 2024-05-27 | 2024-05-27 | TF | 22885 | 22885 |  | 17512.6 | 17512.6 |  |  | N/A | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-27
| MEALS AND SNACKS FOR THE CONDUCT OF OCCULAR INSPECTION FOR RENEWAL OF 5 ASSESSMENT CENTERS |  | No | NP-53.9 - Small Value Procurement | 2024-04-23 | 2024-04-23 |  | 2024-04-23 | 2024-04-23 | 2024-04-23 |  | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-23 | 2024-04-24 | 2024-04-24 |  |  | 2024-04-25 | 2024-04-25 | TF | 9000 | 9000 |  | 9000 | 9000 |  |  | N/A | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-24
| SNACKS FOR DISTRIBUTION OF TOOLKITS OF STEP BENIFICIARIES (MANUHAY, ZSP) |  | No | NP-53.9 - Small Value Procurement | 2024-04-22 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-22 | 2024-04-23 | 2024-04-23 |  |  | 2024-04-23 | 2024-04-23 | TF | 3000 | 3000 |  | 3000 | 3000 |  |  | N/A | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-23
| SNACKS FOR TRAINING OF TRAINERS (TOT) IN PH INSTALLATION NC II @ ZSPI, KABASALAN, ZSP |  | No | NP-53.9 - Small Value Procurement | 2024-05-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-02 | 2024-05-02 |  |  |  | 2024-05-02 | 2024-05-03 | 2024-05-03 |  |  | 2024-05-05 | 2024-05-05 | TF | 37500 | 37500 |  | 37500 | 37500 |  |  | N/A | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-05
| CONSUMABLES FOR TWSP PLUMBING NC I |  | No | NP-53.9 - Small Value Procurement | 2024-05-25 | 2024-05-25 |  | 2024-05-25 | 2024-05-25 | 2024-05-25 |  | 2024-05-25 | 2024-05-25 | 2024-05-25 |  |  |  | 2024-03-26 | 2024-03-29 | 2024-03-29 |  |  | 2024-06-25 | 2024-06-25 | TF | 392485 | 392485 |  | 254950 | 254950 |  |  | N/A | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-06-25
| MEALS AND SNACKS FOR THE CONDUCT OF OCCULAR INSPECTION FOR ASSESSMENT CENTERS AND 9 UTPRAS REGISTRATION | MEALS AND SNACKS FOR THE CONDUCT OF OCCULAR INSPECTION FOR ASSESSMENT CENTERS AND 9 UTPRAS REGISTRATION | No | NP-53.9 - Small Value Procurement | 2024-02-26 | 2024-02-26 | 0 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 0 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 0 | 0 | 0 | 2024-02-27 | 2024-03-01 | 2024-03-01 | 3 | 4 | 2024-03-01 | 2024-03-01 | TF | 17150 | 17150 |  | 17150 | 17150 |  | 0 | N/A | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-03-01 | Ongoing Procurement Process | -241
310300100001000 | CONSUMABLES TOOLS AND EQUIPMENT FOR BARTENDING NC II | EDWIN P. BAYLON JR. | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-03-22 | 0 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 0 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 0 | 0 | 0 | 2023-03-25 | 2024-03-28 | 2024-03-02 | 343 | -20 | N/A | N/A | Government of the Philippines (current year's budget) | 132479 | 132479 |  | 127315 | 127315 |  | 3.898% | N/A | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | N/A | Ongoing Procurement Process | -266
310300100001000 | MATERIALS FOR EIM NC II ( TTSP-25 TRAINEES) | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | 2024-05-24 | 2024-05-24 | 0 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 0 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 0 | 0 | 0 | 2024-05-27 | 2024-05-30 | 2024-05-30 | 3 | 6 | N/A | N/A | Government of the Philippines (current year's budget) | 194800 | 194800 |  | 175100 | 175100 |  | 10.11% | N/A | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | N/A | Ongoing Procurement Process | -329
310300100001000 | SPORTING GOODS FOR PHYSICAL EDUCATION CLASS (EXERICES-BASED FITNESS ACTIVITIES) UNDER DIPLOMA PROGRAM | RONEYRICK JOHN D. ELLOREG | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-03-22 | 0 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 0 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 0 | 0 | 0 | 2024-03-25 | 2024-03-28 | 2024-03-28 | 3 | 6 | 2024-05-27 | 2024-05-27 | Government of the Philippines (current year's budget) | 66260 | 66260 |  | 59400 | 59400 |  | 0.10353 | N/A | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-05-27 | Ongoing Procurement Process | -266
310300100001000 | SUPPLIES, TOOLS, AND EQUIPMENT FOR TILES SETTING ASSESSMENT CENTER ACCCREDITATION INSPECTION PURPOSES | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-12 | 2023-12-12 |  |  |  | 2023-12-13 | 2023-12-18 | 2023-12-18 |  |  | 2024-07-17 | 2024-07-17 | Government of the Philippines (current year's budget) | 155900 | 155900 |  | 155900 | 155900 |  |  | N/A | 2023-12-12 | 2023-12-12 | 2023-12-12 | 2023-12-12 | 2023-12-12 | 7/17/24 | Ongoing Procurement Process
310300100001000 | PLUMBING NC I AND NC II LACKING TOOLS, EQUIPMENT AND MATERIALS - UTPRAS | PHILIP D. TRAYVILLA | No | NP-53.9 - Small Value Procurement | 2023-11-11 | 2023-11-11 |  | 2023-11-11 | 2023-11-11 | 2023-11-11 |  | 2023-11-11 | 2023-11-11 | 2023-11-11 |  |  |  | 2023-12-12 | 2023-12-15 | 2023-12-15 |  |  | N /A | N/A | Government of the Philippines (current year's budget) | 231443 | 231443 |  | 228590 | 228590 |  |  | N/A | 2023-11-11 | 2023-11-11 | 2023-11-11 | 2023-11-11 | 2023-11-11 | N/A | Ongoing Procurement Process
310300100001000 | ASSESSMENT CONSUMABLES FOR EPAS-DIPLOMA (25-DECT,25-DEET) | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | 2024-05-13 | 2024-05-13 |  |  |  | 2024-05-14 | 2024-05-17 | 2024-05-17 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 46550 | 46550 |  | 40808 | 40808 |  |  | N/A | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-05-13 | N/A | Ongoing Procurement Process
310300100001000 | SUPPLIES, TOOLS, AND EQUIPMENT FOR TILES SETTING ASSESSMENT CENTER ACCCREDITATION INSPECTION PURPOSES | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | 2024-06-04 | 2024-06-04 |  | 2024-06-04 | 2024-06-04 | 2024-06-04 |  | 2024-06-04 | 2024-06-04 | 2024-06-05 |  |  |  | 2024-06-10 | 2024-06-10 | 2024-06-10 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 900000 | 900000 |  | 690566 | 690566 |  |  | N/A | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04 | N/A | Ongoing Procurement Process
310300100001000 | MEALS AND SNACKS FOR THE CONDUCT OF OCCULAR INSPECTION FOR ASSESSMENT CENTERS AND 9 UTPRAS REGISTRATION | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-02-26 | 2024-02-26 |  | 2024-02-26 | 2024-02-26 | 2024-02-26 |  | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 | 2024-03-01 | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 | Government of the Philippines (current year's budget) | 17150 | 17150 |  | 17150 | 17150 |  |  | N/A | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-03-01 | Ongoing Procurement Process
310300100001000 | CONSUMABLES FOR TWSP PLUMBING NC I | PHILIP D. TRAYVILLA | No | NP-53.9 - Small Value Procurement | 2024-03-25 | 2024-03-25 | 0 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 0 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 0 | 0 | 0 | 2024-03-26 | 2024-03-29 | 2024-03-29 | 3 | 4 | 2024-06-25 | 2024-06-25 | Government of the Philippines (current year's budget) | 392485 | 392485 |  | 254950 | 254950 |  | 0.35042 | N/A | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-06-25 | Ongoing Procurement Process | -269
310300100001000 | SNACKS FOR DISTRIBUTION OF TOOLKITS OF STEP BENIFICIARIES (MANUHAY, ZSP) | PRESCO P. CAÑETE JR. | No | NP-53.9 - Small Value Procurement | 2024-04-22 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-22 | 2024-04-23 | 2024-04-23 |  |  | 2024-04-23 | 2024-04-23 | Government of the Philippines (current year's budget) | 3000 | 3000 |  | 3000 | 3000 |  |  | N/A | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-23 | Ongoing Procurement Process
310300100001000 | MEALS AND SNACKS FOR THE CONDUCT OF OCCULAR INSPECTION FOR RENEWAL OF 5 ASSESSMENT CENTERS | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-04-23 | 2024-04-23 |  | 2024-04-23 | 2024-04-23 | 2024-04-23 |  | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-23 | 2024-04-24 | 2024-04-24 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 9000 | 9000 |  |  | N/A | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-24 | Ongoing Procurement Process
310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NC II- 50 CANDIDATES | AMY N. MABATID | No | NP-53.9 - Small Value Procurement | 2024-05-24 | 2024-05-24 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 |  | 2024-05-24 | 2024-05-24 | 2024-05-24 |  |  |  | 2024-05-27 | 2024-05-27 | 2024-05-27 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philippines (current year's budget) | 22885 | 22885 |  | 17512.6 | 17512.6 |  |  | N/A | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-27 | Ongoing Procurement Process
310300100001000 | MEALS AND SNACKS FOR CHED EVALUATION AND INVENTORY | MA. EVELYN T. TUBAN | No | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-02 | 2024-04-05 | 2024-04-05 |  |  | 2024-04-06 | 2024-04-06 | Government of the Philippines (current year's budget) | 20250 | 20250 |  | 20250 | 20250 |  |  | N/A | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | Ongoing Procurement Process
310300100001000 | SNACKS FOR 3D PRINTING WORKSHOP/SEMINAR | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2024-05-20 | 2024-05-20 |  | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-05-20 | 2024-05-20 | 2024-05-20 |  |  |  | 2024-05-20 | 2024-05-21 | 2024-05-21 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 6000 | 6000 |  |  | N/A | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-24 | Ongoing Procurement Process
310300100001000 | MEALS AND SNACKS FOR STAR/SEAL OF INTERGRITY ORIENTATION | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 |  |  |  | 2024-05-23 | 2024-05-24 | 2024-05-24 |  |  | 2024-05-25 | 2024-05-25 | Government of the Philippines (current year's budget) | 22500 | 22500 |  | 22500 | 22500 |  |  | N/A | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-25 | Ongoing Procurement Process
310300100001000 | DINNER FOR CENTRAL OFFICE PERSONNEL VISIT | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 |  |  |  | 2024-05-14 | 2024-05-15 | 2024-05-15 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philippines (current year's budget) | 6560 | 6560 |  | 6560 | 6560 |  |  | N/A | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-16 | Ongoing Procurement Process
310300100001000 | ELECTRICAL REPAIR AND MAINTENANCE OF ZSPI | RHANDO O. SANGCOM | No | NP-53.9 - Small Value Procurement | 2023-04-23 | 2023-04-23 |  | 2023-04-23 | 2023-04-23 | 2023-04-23 |  | 2023-04-23 | 2023-04-23 | 2023-04-23 |  |  |  | 2024-04-24 | 2024-04-29 | 2024-04-29 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 844140 | 844140 |  | 820700 | 820700 |  |  | N/A | 2023-04-23 | 2023-04-23 | 2023-04-23 | 2023-04-23 | 2023-04-23 | N/A | Ongoing Procurement Process
310300100001000
310300100001000 | SNACKS FOR TRAINING OF TRAINERS (TOT) IN PH INSTALLATION NC II @ ZSPI, KABASALAN, ZSP | ROMEE A. TAMSI | No | NP-53.9 - Small Value Procurement | 2024-05-02 | 2024-05-02 | 0 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 0 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 0 | 0 | 0 | 2024-05-03 | 2024-05-02 | 2024-05-02 | -1 | 0 | 2024-05-03 | 2024-05-03 | Government of the Philippines (current year's budget) | 37500 | 37500 |  | 37500 | 37500 |  | 0 | N/A | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-05 | Ongoing Procurement Process | -307
[7 empty] | 0 | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 3108902 | 3108902 | 0 | 2692801.6 | 2692801.6 | 0 | 11.88%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | SGD | [10 empty] | SGD | [15 empty] | SGD
|  | LYNDRE G. BAYOTAS | [9 empty] | ANALYN J. ELLIORIN, Ed.D | [16 empty] | GLADYS A. TIONGCO, Ed.D.
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity
Formulas:
Sub/ Open of Bids6 = Complete[[#This Row],[Pre-bid Conf]]

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 21211899.48
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 229
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 33.6364 | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 1.504 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.4348 | 7.0281 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 6 | 0 | 0 | 0 | 0% |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 1 | 1 | 173490 | 83625 | 100% | 48.2% | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 11 | 11 | 2378558 | 2058152 | 100% | 86.53% | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 250 | 216 | 21907961.76 | 19050712.48 | 86.4% | 86.96% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 1 | 1 | 23120 | 19410 | 100% | 83.95% | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 269 | 229 | 24483129.76 | 24483129.76 | 77.28% | 76.41% | 0 | 0
Total for Alternative Mode of Procurement | 269 | 229 | 24483129.76 | 21211899.48 | 77.28% | 76.41% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 239 | 92.64% | 21598191.17 | 87.36% | 18911060.72 | 87.47% | 0.12441
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 19 | 7.364% | 3126052 | 12.64% | 2709951.6 | 12.53% | 0.13311
Total | 258 | 100% | 24724243.17 | 100% | 21621012.32 | 100% | 0.12551
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 269 | 24744243.17
Total | 269 | 24744243.17
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell