## app
|  | Zamboanga Sibugay Polytechnic Institute 2nd Semester Supplemental Annual Procurement Plan for FY 2024 | [11 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
310300100001000 | SUPPLIES AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (FASHION TECHNOLOGY) | MALARE P. COTEJO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2023-09-26 | 2023-09-29 | GoP | 144723 | 144723 |  | FOR REGIONAL SKILLS COMPETITION 2023
'310300100001000 | CONSUMABLES FOR CASHIER 'S OFFICE RAILINGS | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-02-06 | 2024-02-09 | GoP | 49750 | 49750 |  | FOR CASHIER 'S OFFICE RAILINGS
'310300100001000 | CONSUMABLES FOR STAR VALIDATION | ANALYN J. ELLORIN | NO | NP-53.9 - Small Value Procurement | N/A | N/A | N/A | 2024-04-17 | GoP | 14080 | 14080 |  | FOR STAR VALIDATION
'310300100001000 | MATERIALS FOR GREEN TVET PROJECTS | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-04-16 | 2024-04-19 | GoP | 104750 | 104750 |  | FOR GREEN TVET PROJECTS
'310300100001000 | MATERIALS FOR REPAIR CONCRETE FENCE INFRONT OF ADMIN BUILDING | EDEN A. MONGCOPA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-27 | 2024-06-28 | GoP | 45000 | 32450 |  | FOR REPAIR OF CONCRETE FENCE IN FRONT OF ADMIN BUILDING
'310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FORM EIM NC II -(TWSP 50) | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-05-15 | 2024-05-16 | GoP | 20450 | 20450 |  | ASSESSMENT USE
'310300100001000 | I.T. EQUIPMENT FOR TRAINING AND SEMINARS | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-11 | 2024-06-11 | GoP | 560000 | 560000 |  | I.T. EQUIPMENT FOR TRAINING AND SEMINARS
'310300100001000 | TRAINING CONSUMABLES AND EQUIPMENT FOR PHILIPPINE NATIONAL SKILLS COMPETITION 2024 (FASHION TECHNOLOGY) | JUVELYN M. JAUKAL | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-04-05 | 2024-05-08 | GoP | 145400 | 145400 |  | FOR PHILIPPINE NATIONAL SKILLS COMPETITION 2024
'310300100001000 | CONSUMABLES FOR COOKERY ASSESSMENT - DIPLOMA 25 DHMT 2ND YR | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-03-18 | 2024-03-21 | GoP | 47225 | 47225 |  | ASSESSMENT USE
'310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES BPP NCII -50 CANDIDATES (ICT BUUG/TUGOP NHS/IPIL NHS) | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-05-24 | 2024-05-27 | GoP | 22885 | 22885 |  | ASSESSMENT USE
'310300100001000 | NATIONAL ASSESSMENT USED IN CSS (TTSP/TWSP-40 CANDIDATES) | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-05-16 | 2024-05-20 | GoP | 12500 | 12500 |  | ASSESSMENT USE
'310300100001000 | SUPPLIES TOOLS AND EQUIPMENT FOR REGIONAL SKILLS COMPETITION 2023 (ELECTRICAL) | RONNEL B. PEPINO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-09-26 | 2024-09-29 | GoP | 116400 | 116400 |  | FOR REGIONAL SKILLS COMPETITION 2023
'310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR BPP NC II DFPSMT III / DHMT III | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-07-17 | 2024-07-18 | GoP | 8450 | 8450 |  | FOR BPP NC II DFPSMT III / DHMT III
'310300100001000 | MATERIALS FOR ELECTRICAL AND ELECTRONICS BUILDING | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-02-22 | 2024-02-26 | GoP | 49000 | 49000 |  | FOR ELECTRICAL AND ELECTRONICS BUILDING
'310300100001000 | MATERIAL AND EQUIPMENT FOR CARPENTRY NC II, MASONRY I AND NC II - ASSESSMENT PURPOSE | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-03 | 2024-06-06 | GoP | 49400 | 49400 |  | ASSESSMENT USE
'310300100001000 | NATIONAL COMPETENCY ASSESSMENT CONSUMABLES FOR EIM NC II (REGULAR /WALK-IN) | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-04-06 | 2024-04-10 | GoP | 29300 | 29300 |  | ASSESSMENT USE
'310300100001000 | FILLING MATERIALS FOR THE PARKING AREA BETWEEN ZSPI/INNOVATION CENTER AND ZSPI CANTEEN | PRESCO P. CAÑETE JR. | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-08-12 | 2024-08-15 | GoP | 49500 | 49500 |  | FILLING MATERIALS FOR PARKING AREA
AS | MATERIALS FOR UTPRAS INSPECTION (PLUMBING NC II) | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-03 | 2024-06-05 | GoP | 1750 | 1750 |  | FOR UTPRAS INSPECTION
'310300100001000 | ADDITIONAL MATERIALS, TOOLS AND EQUIPMENT FOR PNSC 2024(RESTAURANT SERVICES) | MAY P. COMEDIDO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-07-18 | 2024-07-22 | GoP | 37344 | 37344 |  | FOR PNSC 2024
'310300100001000 | TILLING MATERIALS FOR INNOVATION CENTER | PRESCO P. CAÑETE JR. | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-09-17 | 2024-09-20 | GoP | 238500 | 238500 |  | FOR INNOVATION CENTER
'310300100001000 | INSTALLATION OF SATELITE INTERNET CONSTELLATION IN THE ZSPI FUNCTION HALL | PRESCO P. CAÑETE JR. | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-07-26 | 2024-07-29 | GoP | 45000 | 45000 |  | INSTALLATION OF SATELITE INTERNET CONSTELLATION
'310300100001000 | IMPROVERMENT FOR TRAINING (INNOATION CENTER) CANOPY | PRESCO P. CAÑETE JR. | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-08-19 | 2024-08-22 | GoP | 205550 | 205550 |  | FOR TRAINING (INNOVATION CENTER) CANOPY
'310300100001000 | CONSUMABLES FOR COOCKERY NC II ASSESSMENT- DIPLOMA | AMY N. MABATID | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-07-12 | 2024-07-15 | GoP | 44350 | 44350 |  | ASSESSMENT USE
'310300100001000 | CONSUMABLES, TOOLS, AND EQUIPMENT FOP PHILIPPINE NATIONAL SKILLS COMPETITION 2024 (BAKERY) | AILEENE A. DACULA | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-02-06 | 2024-02-09 | GoP | 329961 | 329961 |  | NATIONAL SKILLS COMPETITION 2024
'310300100001000 | MATERIALS FOR PARKING AREA ROOF REPAIR | ASIRAH B. AMIL | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-07 | 2024-06-10 | GoP | 48450 | 48450 |  | FOR PARKING AREA ROOF REPAIR
'310300100001000 | DEVICE FOR BSRS DIPLOMA PROGRAMS | ROMEE A. TAMSI | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-03-22 | 2024-03-25 | GoP | 960000 | 960000 |  | FOR BSRS DIPLOMA PROGRAMS
'310300100001000 | INSTALLATION OF SATELITE INTERNET CONSTELLATION IN THE ZSPI ADMIN BUILDING | MAE JANE G. DAGUPAN | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-14 | 2024-06-17 | GoP | 45000 | 45000 |  | INSTALLATION OF SATELITE INTERNET CONSTELLATION
'310300100001000 | TOOLS, EQUIPMENT AND TRAINING, CONSUMABLES FOR PHILIPPINE NATIONAL SKILLS COMPETITION 2024 (SKILL AREA, RESTAURANT SERVICE | MAY P. COMEDIDO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-01-31 | 2024-01-31 | GoP | 112858 | 112858 |  | FOR PHILIPPINE NATIONAL SKILLS COMPETITION 2024
'310300100001000 | TOOLS, EQUIPMENT, AND TRAINING CONSUMABLES FOR THE PHILIPPINE NATIONAL SKILLS COMPETITION 2024 (SKILLS AREA: RESTAURANT) | MAY P. COMEDIDO | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-01-31 | 2024-02-05 | GoP | 43320 | 43320 |  | FOR THE PHILIPPINE NATIONAL SKILLS COMPETITION 2024
|  |  | YES | Competitive Bidding | Indicate Date | Indicate Date | Indicate Date | Indicate Date |  | 0
|  |  | NO | Limited Source Bidding | Indicate Date | Indicate Date | Indicate Date | Indicate Date |  | 0
|  |  | NO | Direct Contracting | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | Repeat Order | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | Shopping | Indicate Date | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.1 Two Failed Biddings | Indicate Date | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.2 Emergency Cases | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.3 Take-Over of Contracts | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.4 Adjacent or Contiguous | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.7 Highly Technical Consultants | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.8 Defense Cooperation Agreement | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.9 - Small Value Procurement | Indicate Date | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.11 NGO Participation | Indicate Date | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.12 Community Participation | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | N/A | N/A | Indicate Date | Indicate Date |  | 0
|  |  | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | Indicate Date | Indicate Date |  | 0

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement